## List (hidden)
Not started
On going
Completed
Dropped
Delay

## Estate Operations (hidden)
# | Sequence of Event | PIC | When | Target Completion | eFACT | WB Upstream | New Checkroll (include BKM & KKK) | BPC | Estate Master Data Hierarchy | Estate Operational Metric | Remarks
1 | Business or S/4Hana requirement gathering | Functional | Feb'26 |  | Completed | On going | Completed | On going | On going | On going | - DOTMS in Estate covered by MNT - eBAPA on hold until the eBAPA go live (so far agreed scope & requirement from business sponsor only want to cover BAPA digitalization process, no interface to SAP as of now) - WB Upstream process will follow STPIM timeline & progress
2 | Detail design discussion for existing and new integration | Functional | Feb'26 |  | On going |  | On going | On going
3 | Master data changes discussion (global) | EDM | Feb'26
4 | Master data changes discussion (non China) | EDM | Feb'26
5 | Detail design for application changes requirement | Connected app | Feb'26
6 | Detail timeline alignment discussion for rollout readiness | Connected app | Feb'26
7 | Project timeline from connected application | Connected app | Mar'26
8 | Prioritization of the build (EDM) | EDM | Mar'26
9 | Prioritization of the build | Connected app | Mar'26
10 | Interim solution driven by normal migration scenario | All | Apr'26
11 | Interim solution driven by technology/integration | All | Apr'26
12 | Interim solution driven by business process change | All | Apr'26
13 | BSDD for main stream | Functional | May'26 |  |  |  | On going | On going
14 | BSDD for interim procedure | Functional | May'26
15 | FS by connected application team | Connected app | Jun'26
16 | Build and implemented for connected app (new application) | Connected app | Jun'26
17 | Build for connected application team (new requirement from S/4) | Connected app | Jul'26
18 | Build integration | Connected app | Sep'26
19 | SIT | All | Dec'26
20 | UAT | All | Apr'27
21 | Business simulation | All | Jun'27
22 | Training new features for connected app | Connected app | Jun'27
Note on B2: Novita Lugina: Based on blueprint design

## Asset Maint (hidden)
# | Sequence of Event | PIC | When | Target Completion | DOTMS | KUBE | eBAST | Remarks
1 | Business or S/4Hana requirement gathering | Functional | Feb'26 |  | Completed | Completed | On going | CILT, MIGLI, MES, Supervisory Module & AIMS - Not in MNT S4HANA Scope KUBE - for PM Master Data Request KUBE - For Billing Ticketing will be under OTB Team.
2 | Detail design discussion for existing and new integration | Functional | Feb'26 |  | On going | On going | On going
3 | Master data changes discussion (global) | EDM | Feb'26
4 | Master data changes discussion (non China) | EDM | Feb'26
5 | Detail design for application changes requirement | Connected app | Feb'26 |  | On going |  | On going
6 | Detail timeline alignment discussion for rollout readiness | Connected app | Feb'26 |  |  |  | On going
7 | Project timeline from connected application | Connected app | Mar'26 |  |  |  | Not started
8 | Prioritization of the build (EDM) | EDM | Mar'26
9 | Prioritization of the build | Connected app | Mar'26
10 | Interim solution driven by normal migration scenario | All | Apr'26
11 | Interim solution driven by technology/integration | All | Apr'26
12 | Interim solution driven by business process change | All | Apr'26
13 | BSDD for main stream | Functional | May'26
14 | BSDD for interim procedure | Functional | May'26
15 | FS by connected application team | Connected app | Jun'26
16 | Build and implemented for connected app (new application) | Connected app | Jun'26
17 | Build for connected application team (new requirement from S/4) | Connected app | Jul'26
18 | Build integration | Connected app | Sep'26
19 | SIT | All | Dec'26
20 | UAT | All | Apr'27
21 | Business simulation | All | Jun'27
22 | Training new features for connected app | Connected app | Jun'27
Note on B2: Novita Lugina: Based on blueprint design

## P2P (hidden)
# | Sequence of Event | PIC | When | Target Completion | LIS | Mill digitalization | IDSP | LIMS | Quality Window | eFACT | Remarks
1 | Business or S/4Hana requirement gathering | Functional | Feb'26 |  | On going | Completed | Completed | On going | Not started | On going
2 | Detail design discussion for existing and new integration | Functional | Feb'26 |  | Completed | Completed | Completed | On going | Not started | On going
3 | Master data changes discussion (global) | EDM | Feb'26
4 | Master data changes discussion (non China) | EDM | Feb'26
5 | Detail design for application changes requirement | Connected app | Feb'26 |  | Not started
6 | Detail timeline alignment discussion for rollout readiness | Connected app | Feb'26 |  | Not started
7 | Project timeline from connected application | Connected app | Mar'26 |  | On going
8 | Prioritization of the build (EDM) | EDM | Mar'26
9 | Prioritization of the build | Connected app | Mar'26
10 | Interim solution driven by normal migration scenario | All | Apr'26
11 | Interim solution driven by technology/integration | All | Apr'26
12 | Interim solution driven by business process change | All | Apr'26
13 | BSDD for main stream | Functional | May'26
14 | BSDD for interim procedure | Functional | May'26
15 | FS by connected application team | Connected app | Jun'26
16 | Build and implemented for connected app (new application) | Connected app | Jun'26
17 | Build for connected application team (new requirement from S/4) | Connected app | Jul'26
18 | Build integration | Connected app | Sep'26
19 | SIT | All | Dec'26
20 | UAT | All | Apr'27
21 | Business simulation | All | Jun'27
22 | Training new features for connected app | Connected app | Jun'27
Note on G1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Decoupled from roll out
Note on B2: Novita Lugina: Based on blueprint design
Note on G2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dropped. MES not ready for Go Live. No Definite timeline

## TMS (hidden)
# | Sequence of Event | PIC | When | Target Completion | SmartWB | DOTMS | New Checkroll | eBAST | WB US | WB DS | COPS | iLOGS | JIMS | MIGLI | WB Oleo | Remarks
1 | Business or S/4Hana requirement gathering | Functional | Feb'26 |  | On going | On going | Not started | Not started | Not started | Not started | On going | On going | On going | Not started | Not started | COUPA integration is propose to be dropped.
2 | Detail design discussion for existing and new integration | Functional | Feb'26 |  |  | On going
3 | Master data changes discussion (global) | EDM | Feb'26
4 | Master data changes discussion (non China) | EDM | Feb'26
5 | Detail design for application changes requirement | Connected app | Feb'26 |  |  | On going
6 | Detail timeline alignment discussion for rollout readiness | Connected app | Feb'26
7 | Project timeline from connected application | Connected app | Mar'26
8 | Prioritization of the build (EDM) | EDM | Mar'26
9 | Prioritization of the build | Connected app | Mar'26
10 | Interim solution driven by normal migration scenario | All | Apr'26
11 | Interim solution driven by technology/integration | All | Apr'26
12 | Interim solution driven by business process change | All | Apr'26
13 | BSDD for main stream | Functional | May'26
14 | BSDD for interim procedure | Functional | May'26
15 | FS by connected application team | Connected app | Jun'26
16 | Build and implemented for connected app (new application) | Connected app | Jun'26
17 | Build for connected application team (new requirement from S/4) | Connected app | Jul'26
18 | Build integration | Connected app | Sep'26
19 | SIT | All | Dec'26
20 | UAT | All | Apr'27
21 | Business simulation | All | Jun'27
22 | Training new features for connected app | Connected app | Jun'27
Note on B2: Novita Lugina: Based on blueprint design
Note on J2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Cons Joseph Utama should we change it to on-going? Seharusnya diskusi sudah dimulai yang di inisiasi oleh Pak Eko?

## Trading (hidden)
# | Sequence of Event | PIC | When | Target Completion | LIS | SmartWB | WB US | WB DS | iLOGS | WB Socimas | LIMS | Quality Window | COPS | JIMS | Remarks
1 | Business or S/4Hana requirement gathering | Functional | Feb'26 |  | Not started | Not started | On going | Not started | On going | Not started | Not started | Not started | Not started | Not started
2 | Detail design discussion for existing and new integration | Functional | Feb'26
3 | Master data changes discussion (global) | EDM | Feb'26
4 | Master data changes discussion (non China) | EDM | Feb'26
5 | Detail design for application changes requirement | Connected app | Feb'26 |  | Not started |  |  | Not started |  | Not started
6 | Detail timeline alignment discussion for rollout readiness | Connected app | Feb'26 |  | Not started |  |  | Not started |  | Not started
7 | Project timeline from connected application | Connected app | Mar'26 |  | On going |  |  | Not started |  | Not started
8 | Prioritization of the build (EDM) | EDM | Mar'26
9 | Prioritization of the build (application) | Connected app | Mar'26
10 | Interim solution driven by normal migration scenario | All | Apr'26
11 | Interim solution driven by technology/integration | All | Apr'26
12 | Interim solution driven by business process change | All | Apr'26
13 | BSDD for main stream | Functional | May'26
14 | BSDD for interim procedure | Functional | May'26
15 | FS by connected application team | Connected app | Jun'26
16 | Build and implemented for connected app (new application) | Connected app | Jun'26
17 | Build for connected application team (new requirement from S/4) | Connected app | Jul'26
18 | Build integration | Connected app | Sep'26
19 | SIT | All | Dec'26
20 | UAT | All | Apr'27
21 | Business simulation | All | Jun'27
22 | Training new features for connected app | Connected app | Jun'27
Note on B2: Novita Lugina: Based on blueprint design

## STPIM (hidden)
# | Sequence of Event | PIC | When | Target Completion | WB US | eFACT | New Checkroll | eBAST | DOTMS | WB DS | BASYS | iLOGS | ASRS | Coupa | KUBE | Remedy | ePO | Smart Trace | BPC | Mass Balance | Vendor Evaluation | WB oleo/socimas | Remarks
1 | Business or S/4Hana requirement gathering | Functional | Feb'26 |  | On going | On going | Not started | On going | On going | On going | On going | On going | Not started | On going | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
2 | Detail design discussion for existing and new integration | Functional | Feb'26 | [10 empty] | On going
3 | Master data changes discussion (global) | EDM | Feb'26 | [10 empty] | On going
4 | Master data changes discussion (non China) | EDM | Feb'26
5 | Detail design for application changes requirement | Connected app | Feb'26 | [7 empty] | On going |  |  | On going
6 | Detail timeline alignment discussion for rollout readiness | Connected app | Feb'26 | [7 empty] | Not started
7 | Project timeline from connected application | Connected app | Mar'26 | [7 empty] | Not started |  |  | On going
8 | Prioritization of the build (EDM) | EDM | Mar'26
9 | Prioritization of the build | Connected app | Mar'26 | [10 empty] | On going
10 | Interim solution driven by normal migration scenario | All | Apr'26
11 | Interim solution driven by technology/integration | All | Apr'26
12 | Interim solution driven by business process change | All | Apr'26
13 | BSDD for main stream | Functional | May'26
14 | BSDD for interim procedure | Functional | May'26
15 | FS by connected application team | Connected app | Jun'26
16 | Build and implemented for connected app (new application) | Connected app | Jun'26
17 | Build for connected application team (new requirement from S/4) | Connected app | Jul'26
18 | Build integration | Connected app | Sep'26
19 | SIT | All | Dec'26
20 | UAT | All | Apr'27
21 | Business simulation | All | Jun'27
22 | Training new features for connected app | Connected app | Jun'27
Note on H1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Reservation Beras
Note on R1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: inside SAP
Note on B2: Novita Lugina: Based on blueprint design
Note on J2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Next: DotMS Stock Opname
Note on L2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Target initial discussion: Thu, 2 Oct

## OTB (hidden)
# | Sequence of Event | PIC | When | Target Completion | DAMIMAS | IDSP/IOM | Doc Tracking | KUBE | WB US | ILOGS | E-BAST | Remarks
1 | Business or S/4Hana requirement gathering | Functional | Feb'26 |  | Not started | Not started | Completed | Completed | Completed | Completed | Completed
2 | Detail design discussion for existing and new integration | Functional | Feb'26 |  | Not started | Not started | Completed | Completed | Completed | Completed | Completed
3 | Master data changes discussion (global) | EDM | Feb'26
4 | Master data changes discussion (non China) | EDM | Feb'26
5 | Detail design for application changes requirement | Connected app | Feb'26 |  |  |  | Not started
6 | Detail timeline alignment discussion for rollout readiness | Connected app | Feb'26 |  |  |  | Not started
7 | Project timeline from connected application | Connected app | Mar'26 |  |  |  | Not started
8 | Prioritization of the build (EDM) | EDM | Mar'26
9 | Prioritization of the build | Connected app | Mar'26 |  |  |  | Not started
10 | Interim solution driven by normal migration scenario | All | Apr'26
11 | Interim solution driven by technology/integration | All | Apr'26
12 | Interim solution driven by business process change | All | Apr'26
13 | BSDD for main stream | Functional | May'26
14 | BSDD for interim procedure | Functional | May'26
15 | FS by connected application team | Connected app | Jun'26
16 | Build and implemented for connected app (new application) | Connected app | Jun'26
17 | Build for connected application team (new requirement from S/4) | Connected app | Jul'26
18 | Build integration | Connected app | Sep'26
19 | SIT | All | Dec'26
20 | UAT | All | Apr'27
21 | Business simulation | All | Jun'27
22 | Training new features for connected app | Connected app | Jun'27
Note on F1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Non Prioirity, Not in Pilot for Damimas
Note on G1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Not priority, Not in Pilot GT Reply: Will be used in R03 and not impact to global design (only send data) Reply: plan: April 2026
Note on B2: Novita Lugina: Based on blueprint design
Note on H2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Meeting on 27-Feb
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Meeting on 2-Mar
Note on K2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Scheduled 27-Feb
Note on H3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Meeting on 27-Feb
Note on I3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Meeting on 2-Mar
Note on K3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Scheduled 27-Feb

## Fin & Accn (hidden)
# | Sequence of Event | PIC | When | Target Completion | eFACT | PL Overview | ProInt | New Checkroll | DiFi | Supplier Financing | Asset Handheld | FR automation | KUBE | Workdays | Coretax | eBANKING | Tungsten | BPC | BW | HEX | LC | Remarks
1 | Business or S/4Hana requirement gathering | Functional | Feb'26 |  | Not started | On going | On going | On going | On going | On going | On going | On going | On going | On going | On going | On going | On going | On going | Not started | Not started | Not started
2 | Detail design discussion for existing and new integration | Functional | Feb'26 |  |  | On going | On going | On going | On going | On going | On going | On going | On going | On going | On going | On going | On going
3 | Master data changes discussion (global) | EDM | Feb'26
4 | Master data changes discussion (non China) | EDM | Feb'26
5 | Detail design for application changes requirement | Connected app | Feb'26 |  |  | On going | On going | On going | On going | On going | On going | On going | On going | On going | On going | On going | On going
6 | Detail timeline alignment discussion for rollout readiness | Connected app | Feb'26 |  |  | On going | On going | On going | On going | On going | On going | On going | On going | On going | On going | On going | On going
7 | Project timeline from connected application | Connected app | Mar'26
8 | Prioritization of the build (EDM) | EDM | Mar'26
9 | Prioritization of the build | Connected app | Mar'26
10 | Interim solution driven by normal migration scenario | All | Apr'26
11 | Interim solution driven by technology/integration | All | Apr'26
12 | Interim solution driven by business process change | All | Apr'26
13 | BSDD for main stream | Functional | May'26
14 | BSDD for interim procedure | Functional | May'26
15 | FS by connected application team | Connected app | Jun'26
16 | Build and implemented for connected app (new application) | Connected app | Jun'26
17 | Build for connected application team (new requirement from S/4) | Connected app | Jul'26
18 | Build integration | Connected app | Sep'26
19 | SIT | All | Dec'26
20 | UAT | All | Apr'27
21 | Business simulation | All | Jun'27
22 | Training new features for connected app | Connected app | Jun'27
Note on B2: Novita Lugina: Based on blueprint design

## MDG
# | Sequence of Event | PIC | When | Target Completion | BI/BW/Data lake | ProInt (New Checkroll) | Coupa | KUBE | WB US | Workday | HEX | WB DS | WB oleo/socimas | CRQ | COPS | JIMS | IDSP-IOM | CILT | Remarks
1 | Business or S/4Hana requirement gathering | Functional | Feb'26 |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
2 | Detail design discussion for existing and new integration | Functional | Feb'26
3 | Master data changes discussion (global) | EDM | Feb'26
4 | Master data changes discussion (non China) | EDM | Feb'26
5 | Detail design for application changes requirement | Connected app | Feb'26
6 | Detail timeline alignment discussion for rollout readiness | Connected app | Feb'26
7 | Project timeline from connected application | Connected app | Mar'26
8 | Prioritization of the build (EDM) | EDM | Mar'26
9 | Prioritization of the build | Connected app | Mar'26
10 | Interim solution driven by normal migration scenario | All | Apr'26
11 | Interim solution driven by technology/integration | All | Apr'26
12 | Interim solution driven by business process change | All | Apr'26
13 | BSDD for main stream | Functional | May'26
14 | BSDD for interim procedure | Functional | May'26
15 | FS by connected application team | Connected app | Jun'26
16 | Build and implemented for connected app (new application) | Connected app | Jun'26
17 | Build for connected application team (new requirement from S/4) | Connected app | Jul'26
18 | Build integration | Connected app | Sep'26
19 | SIT | All | Dec'26
20 | UAT | All | Apr'27
21 | Business simulation | All | Jun'27
22 | Training new features for connected app | Connected app | Jun'27
Note on B2: Novita Lugina: Based on blueprint design

## GRC (hidden)
# | Sequence of Event | PIC | When | Target Completion | US | DSI | CBS | Remarks
1 | Business or S/4Hana requirement gathering | Functional | Feb'26
2 | Detail design discussion for existing and new integration | Functional | Feb'26
3 | Master data changes discussion (global) | EDM | Feb'26
4 | Master data changes discussion (non China) | EDM | Feb'26
5 | Detail design for application changes requirement | Connected app | Feb'26
6 | Detail timeline alignment discussion for rollout readiness | Connected app | Feb'26
7 | Project timeline from connected application | Connected app | Mar'26
8 | Prioritization of the build (EDM) | EDM | Mar'26
9 | Prioritization of the build | Connected app | Mar'26
10 | Interim solution driven by normal migration scenario | All | Apr'26
11 | Interim solution driven by technology/integration | All | Apr'26
12 | Interim solution driven by business process change | All | Apr'26
13 | BSDD for main stream | Functional | May'26
14 | BSDD for interim procedure | Functional | May'26
15 | FS by connected application team | Connected app | Jun'26
16 | Build and implemented for connected app (new application) | Connected app | Jun'26
17 | Build for connected application team (new requirement from S/4) | Connected app | Jul'26
18 | Build integration | Connected app | Sep'26
19 | SIT | All | Dec'26
20 | UAT | All | Apr'27
21 | Business simulation | All | Jun'27
22 | Training new features for connected app | Connected app | Jun'27
Note on B2: Novita Lugina: Based on blueprint design

## List of Application
# | Application Name | List of S/4Hana Streams | Estate Operations | Asset Maint | P2P | TMS | Trading | STPIM | OTB | FIn & Accn | EDM
1 | Remedy/Helix, KUBE | - Asset maintenance - STPIM - Order to bill - Finance & accounting - EDM |  | Completed |  |  |  | Not started | Completed | On going | Not started
2 | Coupa | - Transport & logistics - STPIM - Order to bill - EDM |  |  |  | #REF! |  | On going | #REF! |  | Not started
3 | eFACT | - Estate operation - Plan to produce - STPIM - Finance & accounting | Completed |  | On going |  |  | On going |  | Not started
4 | MES | - Plan to produce - Asset maintenance |  | #REF! | Completed
5 | ProInt | - Finance & accounting | [7 empty] | On going
6 | New Checkroll | - Estate operation - Transport & logistic - STPIM - Finance & accounting - EDM | Completed |  |  | Not started |  | Not started |  | On going | Not started
7 | WB upstream | - Estate operation - Transport & logistic - Trading - STPIM - Order to bill - EDM | On going |  |  | Not started | On going | On going | Completed |  | Not started
8 | SmartWB | - Transport & logistic - Trading |  |  |  | On going | Not started
9 | LIMS | - Plan to produce - Trading |  |  | On going |  | Not started
10 | Ilogs (vendor) | - Transport & logistic - Trading - STPIM |  |  |  | On going | On going | On going | Completed
11 | Workday | - EDM - Finance & accounting | [7 empty] | On going | Not started
12 | Esker | N/A
13 | Agiblock | N/A
14 | IDSP/IOM | - Plan to produce - Order to bill |  |  | Completed |  |  |  | Not started
15 | Dashboard (Power BI / DOMO etc.) | Across all streams
16 | BPC | - Estate operation - Finance & accounting | On going | [6 empty] | On going
17 | BW | - Plan to produce - STPIM - Order to bill - Finance & accounting - EDM |  |  | #REF! |  |  | Not started | #REF! | Not started | Not started
18 | DOTMS | - Estate operation - Transport & logistic - Asset maintenance - STPIM | #REF! | Completed |  | On going |  | On going
19 | Blockchain | - STIPM | [5 empty] | #REF!
20 | HEX | - Plan to produce - STPIM - Order to bill - Finance & accounting - EDM |  |  | #REF! |  |  | #REF! | #REF! | Not started | Not started
21 | BSC | N/A
22 | eBAPA | - Estate operation | #REF!
23 | Estate master data hierarchy | - Estate operation | On going
24 | Estate operational metric | - Estate operation | On going
25 | LIS | - Plan to produce - Trading |  |  | On going |  | Not started
26 | WB downstream | - Transport & logistic - STPIM - Order to bill - EDM |  |  |  | Not started |  | On going |  |  | Not started
27 | WB oleo/socimas | - Transport & logistic - STPIM - Order to bill - EDM |  |  |  | Not started |  | Not started |  |  | Not started
28 | Quality Window | - Plan to produce - Trading |  |  | Not started |  | Not started
29 | e-BAST | - Transport & logistic - Asset maintenance - STPIM |  | On going |  | Not started |  | On going
30 | COPS | - Transport & logistic - Trading |  |  |  | On going | Not started
31 | JIMS | - Transport & logistic - Trading |  |  |  | On going | Not started
32 | MIGLI | - Transport & logistic - Asset maintenance |  | #REF! |  | Not started
33 | CILT | - Asset maintenance |  | #REF!
34 | BASYS | - STPIM | [5 empty] | On going
35 | ASRS (vendor) | - STPIM | [5 empty] | Not started
36 | ePO | - STPIM | [5 empty] | Not started
37 | SmartTrace | - STPIM | [5 empty] | Not started
38 | Mass Balance | - STPIM | [5 empty] | Not started
39 | Vendor evaluation | - STPIM | [5 empty] | Not started
40 | DAMIMAS | - Order to bill | [6 empty] | Not started
41 | Doc tracking | - Order to bill | [6 empty] | Completed
42 | LC | - Finance & accounting | [7 empty] | Not started
43 | PL overview | - Finance & accounting | [7 empty] | On going
44 | DiFi | - Finance & accounting | [7 empty] | On going
45 | Supplier financing | - Finance & accounting | [7 empty] | On going
46 | Asset handheld | - Finance & accounting | [7 empty] | On going
47 | FR automation | - Finance & accounting | [7 empty] | On going
48 | Coretax | - Finance & accounting | [7 empty] | On going
49 | eBanking | - Finance & accounting | [7 empty] | On going
50 | Tungsten | - Finance & accounting | [7 empty] | On going
51 | CRQ | - EDM | [8 empty] | Not started
52 | PTA approval
53 | SPK form
54 | MDG
55 | GRC
56 | AIMS | - Asset maintenance |  | #REF!

## Summary
12 Feb update
Stream | Total Connected Apps | Not started | On-going | Completed
Estate operations | 7 | 4 | 3 | 0
Asset maintenance | 3 | 1 | 0 | 2
P2P | 8 | 4 | 4 | 0
TMS | 11 | 5 | 6 | 0
Trading | 9 | 9 | 0 | 0
STPIM | 17 | 13 | 4 | 0
OTB | 7 | 6 | 1 | 0
Finance & Accounting | 13 | 1 | 12 | 0
MDG | 4
GRC
Update 26 Feb
Stream | Total Connected Apps | Not started | On-going | Completed | Last week not started | This week not started
Estate operations | 8 | 1 | 5 | 2 | 50% | 13%
Asset maintenance | 3 | 1 | 0 | 2 | 33% | 33%
P2P | 9 | 3 | 5 | 1 | 50% | 38%
TMS | 11 | 6 | 5 | 0 | 45% | 42%
Trading | 10 | 10 | 0 | 0 | 100% | 100%
STPIM | 18 | 10 | 8 | 0 | 72% | 65%
OTB | 7 | 3 | 3 | 1 | 86% | 43%
Finance & Accounting | 17 | 4 | 13 | 0 | 29% | 24%
MDG | 14* | 14
GRC | Start to trigger discussion on process control to-be
Update 10 Mar
Stream | Total Connected Apps | Not started | On-going | Completed | Last week not started | This week not started
Estate operations | 6 | 0 | 4 | 2 | 13% | 0%
Asset maintenance | 3 | 0 | 1 | 2 | 33% | 0%
P2P | 5 | 0 | 3 | 2 | 38% | 0%
TMS | 10 | 4 | 6 | 0 | 42% | 40%
Trading | 8 | 6 | 2 | 0 | 100% | 75%
STPIM | 16 | 7 | 8 | 1 | 65% | 43.75%
OTB | 7 | 2 | 0 | 5 | 43% | 28.57%
Finance & Accounting | 11 | 2 | 9 | 0 | 24% | 18.18%
MDG | 12* | 12
GRC | Will further discusss once AI is available for process control

## Activities Definition
Group Activities | Activities | Definition
Requirement + Solutioning | Detail Requirement Gathering | Get full requirement from functional teams for interfaces or enhancement on connected applications
| Connected Apps Solutioning | Design to-be solution with functional teams for all requirements coming from the project
| Master data (global) impact assessment | Master data impact assessment (global master data) on each of the connected applications and discuss for solution during interim period
| Master data (Non China) impact assessment | Master data impact assessment (non-China) on each of the connected applications and discuss for solution during interim period
| Detail design (to-be and interim) | Overall detail design : application enhancement, master data interim solution, and interfaces
Prioritization | Project planning | Development effort estimation for agreed S/4Hana solutions
| Prioritization (Apps & Master Data) | Prioritization of development
Design documentation | Apps FS/BRD/BSDD | Detail design documentation with sign-off from users
Development | Interim automation build | Development of automation for interim solutions based on the agreed solutions
| New and Existing apps build/enhancement | Development of applications/enhancement based on the agreed solutions
| Integration build | Build interface with S/4Hana or ECC if required
Testing | SIT | Integration testing with S/4Hana or other connected applications
| UAT | User acceptance testing
| Biz simulation | End to end business process simulations
Training | Training | End user training based on change management training plan if there's new application or new ways or working on using the application
Implementation | Implementation/rollout | Rollout new solution/development to all units
Create interim tracking separately

## Apps tracking
|  |  | Activities Grouping | Requirement + Solutioning | [10 empty] | Prioritization |  |  |  | Design Documentation |  | Development | [5 empty] | Testing | [5 empty] | Implementation
Main application with potential major change or work required |  |  | Today | 2026-03-24 |  | 2026-03-24 |  | 2026-03-24 |  | 2026-03-24 |  | 2026-03-24 |  |  | 2026-03-24 |  | 2026-03-24 |  | 2026-03-24 |  | 2026-03-24 |  | 2026-03-24 |  | 2026-03-24 |  | 2026-03-24 |  | 2026-03-24 |  | 2026-03-24 |  | 2026-03-24
|  |  | Deadline | 2026-02-28 |  | 2026-02-28 |  | 2026-02-28 |  | 2026-02-28 |  | 2026-02-28 |  |  | 2026-02-28 |  | 2026-03-31 |  | 2026-06-30 |  | 2026-06-30 |  | 2026-06-30 |  | 2026-09-30 |  | 2026-12-31 |  | 2027-04-30 |  | 2027-06-30 |  | 2027-06-30
Application | PIC Apps | PIC Functional | Stream | Detail Requirement Gathering | Highlights/Issue/Risks | Connected Apps Solutioning | Highlights/Issue/Risks | Master data (global) impact assessment | Highlights/Issue/Risks | Master data (Non China) impact assessment | Highlights/Issue/Risks | Detail design (to-be & interim) | Revised target date for detail design + solutioning | Highlights/Issue/Risks | Project planning | Highlights/Issue/Risks | Prioritization (Apps & Master Data) | Highlights/Issue/Risks | Apps FS/BRD/BSDD | Highlights/Issue/Risks | Interim automation build | Highlights/Issue/Risks | New and existing apps build/enhancement | Highlights/Issue/Risks | Integration build | Highlights/Issue/Risks | SIT | Highlights/Issue/Risks | UAT | Highlights/Issue/Risks | Biz simulation | Highlights/Issue/Risks | Training | Highlights/Issue/Risks
Workday | Jimmy | Hendra Setiawan | Finance & accounting | On going | Scope : Travel Posting & Vendor Employee for Indonesia 24/02 : Initial meeting with Faris to share as-sis interface data structure for payroll posting and travel expense 16/03 : Potential To-Be Interim Integration design has been discussed but further assessment need to be done by IT HCM : Split Workday XML into 2 files Next meeting scheduled on 27/03 | On going |  | Not started |  | Not started |  | On going |  |  | On going |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
WB US | Yanpiter | Eko Trisatono + FX Henry | TMS | On going |  | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
WB US |  |  | Trading (ACM) | On going |  | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
WB US |  |  | STPIM | On going |  | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
WB US |  |  | OTB | Completed |  | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
WB US |  |  | MDG | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
WB US |  |  | Estate Operations | On going |  | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
WB Socimas |  |  | Trading (ACM) | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
WB Socimas |  |  | STPIM | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
WB Socimas |  |  | MDG | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
WB Socimas |  |  | TMS | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
WB DS |  |  | TMS | On going |  | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
WB DS |  |  | Trading (ACM) | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
WB DS |  |  | STPIM | On going |  | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
WB DS |  |  | MDG | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
Vendor Evaluation | Edward | Edward | STPIM | Not started | Second priority | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
Tungsten | Keen Thung | Christin | Finance & accounting | On going |  | On going |  | Not started |  | Not started |  | On going |  |  | On going |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
Supplier Financing | Faris | Faris | Finance & accounting | On going |  | On going |  | Not started |  | Not started |  | On going |  |  | On going |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
SmartWB | Nitya | Joseph | TMS | Dropped | Decoupled as SMARTWB won't be in time for S/4 pilot/rollout | Dropped |  | Dropped |  | Dropped |  | Dropped |  |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped
SmartWB |  |  | Trading (ACM) | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped
SmartTrace | Stevan | Edward | STPIM | Not started
SmartTrace |  |  | OTB | Not started
SmartTrace |  |  | Trading (ACM) | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
Quality Window | Steel | Steel | Plan to produce | Dropped | Through manual download and upload only | Dropped |  | Dropped |  | Dropped |  | Dropped |  |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped
Quality Window |  |  | Trading (ACM) | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped
ProInt | Jimmy | Faris | Finance & accounting | On going | Scope : Payroll Posting 24/02 : Initial meeting with Faris to share as-sis interface data structure for payroll posting and travel expense 11/03 : The best possible Interim Payrolll Posting Integration Solution option has been discussed but further assessment need to be done : Integration from PI to IS and Payroll Posting BAPI Simulation Next meeting scheduled on 25/03 | On going |  | Not started |  | Not started |  | On going |  |  | On going |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
PL Overview | Arif | Daniel | Finance & accounting | On going |  | On going |  | Not started |  | Not started |  | On going |  |  | On going |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
New Checkroll (include BKM & KKK) | Pungkie | Suria | Estate Operations | On going |  | On going |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
New Checkroll |  |  | TMS | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
New Checkroll |  |  | STPIM | Not started | For "reservasi beras" Target to discuss in Apr'26 | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
New Checkroll |  |  | Finance & accounting | On going |  | On going |  | Not started |  | Not started |  | On going |  |  | On going |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
New Checkroll |  |  | MDG | On going |  | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
Mill digitalization | Sumario | Steel | Plan to produce | Dropped | Decoupled from S/4Hana pilot and rollout, applications won't be in time for S/4 implementation | Dropped |  | Dropped |  | Dropped |  | Dropped |  |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped
MIGLI | Danny Zhao | Joseph | TMS | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
Mass Balance | Steel | Edward | STPIM | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
LIS | Arif | Steel | Plan to produce | On going | Completed for Mill, pending for KCP, LIS team can start assessing mill requirement | On going |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
LIS |  |  | Trading (ACM) | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
LIMS | Nanda Faris | Steel | Plan to produce | On going |  | On going |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
LIMS |  |  | Trading (ACM) | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
LC | Suyanni | Suyanni | Finance & accounting | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
KUBE | Chua/Alimin | Sonia | Asset Maintenance | Completed |  | On going |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
KUBE |  | Bambang | STPIM | Not started | First discuccion targeted in Apr | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
KUBE |  | Cons Hendry | OTB | Completed |  | Completed |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
KUBE |  | Christin | Finance & accounting | On going |  | On going |  | Not started |  | Not started |  | On going |  |  | On going |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
KUBE (SG Corp) |  | Suyanni | [14 empty] | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
KUBE (SG DS)
KUBE (Sugar)
KUBE |  | Daniel Made | MDG | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
KUBE (SG DS) | [16 empty] | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
JIMS | Joh By | Joseph | TMS | On going |  | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
JIMS |  |  | Trading (ACM) | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
JIMS |  |  | MDG | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
iLOGS | Heikal | Eko + FX Henry | TMS | On going |  | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
iLOGS |  |  | Trading (ACM) | On going |  | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
iLOGS |  |  | STPIM | On going |  | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
ILOGS |  |  | OTB | Completed |  | Completed |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
IDSP/IOM | Joh By | Harmansyah | MDG | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
IDSP/IOM |  |  | OTB | Not started | Non priority, will not be part of rollout, plan to start in Apr'26 | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
IDSP | Joh By | Steel | Plan to produce | Completed |  | Completed |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
FR automation | Arif | Oktavianus Rio/Dewi R. | Finance & accounting | On going |  | On going |  | Not started |  | Not started |  | On going |  |  | On going |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
Estate Operational Metric | Arif | Suria | Estate Operations | On going |  | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
Estate Master Data Hierarchy |  |  | Estate Operations | On going |  | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
ePO | Edward | Edward | STPIM | Dropped | Within SAP and not part of applications | Dropped |  | Dropped |  | Dropped |  | Dropped |  |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped
eFACT | Sumario | Suria | Estate Operations | Completed |  | On going |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
eFACT |  |  | Plan to produce | On going |  | On going |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
eFACT |  |  | STPIM | On going |  | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
eFACT |  |  | Finance & accounting | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
eBAST | Arif | Sonia /Richard | OTB | Completed |  | Completed |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
eBAST |  |  | Asset Maintenance | On going | WSDV is completed. Central Workshop is in progress | On going | WSDV is completed. Central Workshop is in progress | Not started |  | Not started |  | On going |  |  | On going |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
eBAST |  |  | TMS | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
eBAST |  |  | STPIM | On going |  | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
DOTMS | Arif | Sonia | Asset Maintenance | Completed |  | On going |  | Not started |  | Not started |  | On going |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
DOTMS |  |  | TMS | Dropped | Include in Asset Maintenance requirement | Dropped |  | Dropped |  | Dropped |  | Dropped |  |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped
DOTMS |  |  | STPIM | On going | For stock opname requirement Target 1st workshop on 16th Mar | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
Doc Tracking | Arif | Hendry | OTB | Completed |  | Completed |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
DAMIMAS | Grand | Hendry | OTB | Not started | Non priority, will not be part of rollout | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
CRQ | Alimin | Daniel Made | MDG | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
Coupa | Kevin | Edward | STPIM | On going |  | On going |  | On going |  | Not started |  | On going |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
Coupa |  |  | MDG | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
COPS | Joh By | Joseph | TMS | On going |  | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
COPS |  |  | Trading (ACM) | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
COPS |  |  | MDG | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
CILT | Joh By | Daniel Made | MDG | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
BPC | Anton | Suria | Estate Operations | On going |  | On going |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
BPC |  |  | STPIM | On going |  | Not started |  | Not started | Target to discuss on 4th Mar | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
BPC |  |  | Finance & accounting | On going |  | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
BASYS | Arif | Imera | STPIM | On going | Initial discussion targeted on 2nd Mar | Not started |  | Not started |  | Not started |  | On going |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
ASRS | Indra Muliadi | Imera | STPIM | Not started | Target to discuss on 1st April | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
Remedy (SRT) | Alimin | Bambang | STPIM | Not started | First discussion targeted in Apr | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
Agiblocks (EU, LATAM) | Jacky Loke | Faris | Finance & accounting | [13 empty] | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
Agiblocks (Sugar) | Jacky Loke | [15 empty] | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
Esker (EU, LATAM) | Vincent Ow | Faris | Finance & accounting | [13 empty] | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
WB China Agri | 3rd party (Kabin) | Edward | TMS | [13 empty] | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
STPIM
|  |  | Trading (ACM) | [13 empty] | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
TPM (China) | 3rd party (Kabin) | Eve | STPIM | On going |  | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
|  |  | OTB | On going |  | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
|  |  | Finance & accounting | On going |  | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
Port Management (China) | Kabin |  | STPIM | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped
|  |  | OTB | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped
|  |  | Finance & accounting | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped |  | Dropped
HCM payroll (China) | Jimmy | Faris | Finance & accounting | On going | Scope : Payroll Posting for China Food 11/03 : Initial discussion to share as-is SAP HCP payroll posting integration approach to SAP RCP using SAP ALE 17/03 : Potential To-Be Interim Integration design has been discussed but further assessment need to be done by ABAPer : SAP ALE RFC to S/4HANA Next meeting scheduled on 24/03 | Not started |  | Not started |  | Not started |  | Not started |  |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started |  | Not started
Note on A94: Novita Lugina: on development
Note on A95: Novita Lugina: on development
Note on A96: Novita Lugina: on development
Note on A103: Novita Lugina: not developed yet (decoupled?)

## Weekly Status Update
Application Name | PIC Apps | PIC Functional | Status | Remarks | Target Completion Date | Revised Target Date
WB upstream | Yanpiter T. P. Sitompul | Eko Trisatono |  | OTB completed, other stream have dependency on ACM to-be design | 2026-02-01
WB downstream |  |  |  | Dependency on ACM to-be design
LIS | Muhammad Arif Khairiansyah | Adistya Steelciawan |  | On-going discussion for P2P ACM have not started discussion
KUBE | Chua Pooi Leong/Alimin | Sonia (asset maintemance) Bambang (STPIM) Hendry (OTB) Christin (F&A) Suyanni (F&A( Daniel Made Oka (MDG) |  | Asset maintenance & OTB - completed Finance & accounting - on going STPIM & MDG - not started
Estate master data hierarchy | Muhammad Arif Khairiansyah | Suria |  | On going discussion
Estate operational metric | Muhammad Arif Khairiansyah | Suria |  | On going discussion
eFACT | Sumario | Suria |  | Estate operations - completed Plan to produce, STPIM - on going Finance & accounting - not started
eBAST | Muhammad Arif Khairiansyah | Richardus Patrick Sembiring |  | OTB completed asset maintenance & STPIM - on going TMS - not started
DOTMS | Muhammad Arif Khairiansyah | Sonia Helena Ladasi |  | Asset maintenance - completed STPIM - on going
Coupa | Kevin Sudiro Joseputra | Edward Soesanto |  | STPIM - on going MDG - not started
New Checkroll | Pungkie Brahmantyo | Suria |  | Estate operations, finance & accounting, MDG - on going TMS & STPIM - not started
ProInt | Jimmy Naslim | Novrizal Faris Muttaqin |  | Finance & accounting - on going
iLOGS | Heikal Nursa Krisna Dikpa | Eko Trisatono |  | OTB - completed TMS, Trading, STPIM - on going
COPS | Joh By | Joseph |  | TMS - on going Trading & MDG - not started
BPC | Anton Rusdiono Budicahyanto | Suria |  | Estate operations, STPIM, finance & accounting - on going
BASYS | Muhammad Arif Khairiansyah | Imera |  | STPIM - on going

## 1. Requirement gathering (hidden)
# | Application Name | Stream | When | Status | Remarks
1 | Remedy/Helix, KUBE | Asset Maintenance | Feb'26 | Completed
2 | Remedy/Helix, KUBE | STPIM | Feb'26 | Not started
3 | Remedy/Helix, KUBE | OTB | Feb'26 | Completed
4 | Remedy/Helix, KUBE | Fin & Accn | Feb'26 | On going
5 | Remedy/Helix, KUBE | EDM | Feb'26 | Not started
6 | Coupa | TMS | Feb'26 | #REF! | dropped
7 | Coupa | STPIM | Feb'26 | On going
8 | Coupa | OTB | Feb'26 | #REF! | dropped
9 | Coupa | EDM | Feb'26 | Not started
10 | eFACT | Estate Operation | Feb'26 | Completed
11 | eFACT | P2P | Feb'26 | On going
12 | eFACT | STPIM | Feb'26 | On going
13 | eFACT | Fin & Accn | Feb'26 | Not started
14 | MES | Asset Maintenance | Feb'26 | #REF!
15 | Mill digitalization | P2P | Feb'26 | Completed | decoupled
16 | ProInt | Fin & Accn | Feb'26 | On going
17 | New Checkroll | Estate Operation | Feb'26 | Completed
18 | New Checkroll | TMS | Feb'26 | Not started
19 | New Checkroll | STPIM | Feb'26 | Not started
20 | New Checkroll | Fin & Accn | Feb'26 | On going
21 | New Checkroll | EDM | Feb'26 | Not started
22 | WB US | Estate Operation | Feb'26 | On going
23 | WB US | TMS | Feb'26 | Not started
24 | WB US | Trading | Feb'26 | On going
25 | WB US | STPIM | Feb'26 | On going
26 | WB US | OTB | Feb'26 | Completed
27 | WB US | EDM | Feb'26 | Not started
28 | SMART WB | TMS | Feb'26 | On going
29 | SMART WB | Trading | Feb'26 | Not started
30 | LIMS | P2P | Feb'26 | On going
31 | LIMS | Trading | Feb'26 | Not started
32 | iLogs | TMS | Feb'26 | On going
33 | iLogs | Trading | Feb'26 | On going
34 | iLogs | STPIM | Feb'26 | On going
35 | iLogs | OTB | Feb'26 | Completed
36 | Workday | Fin & Accn | Feb'26 | On going
37 | Workday | EDM | Feb'26 | Not started
38 | Esker | N/A | Feb'26
39 | Agiblock | N/A | Feb'26
40 | IDSP/IOM | P2P | Feb'26 | Completed
41 | IDSP/IOM | OTB | Feb'26 | Not started
42 | Dashboard (Power BI / DOMO etc.) | All Streams | Feb'26
43 | BPC | Estate Operation | Feb'26 | On going
44 | BPC | STPIM | Feb'26 | Not started
45 | BPC | Fin & Accn | Feb'26 | On going
46 | BW | P2P | Feb'26 | #REF!
47 | BW | STPIM | Feb'26 | Not started
48 | BW | Fin & Accn | Feb'26 | Not started
49 | BW | OTB | Feb'26 | #REF!
50 | BW | EDM | Feb'26 | Not started
51 | DOTMS | Estate Operation | Feb'26 | #REF!
52 | DOTMS | Asset Maintenance | Feb'26 | Completed
53 | DOTMS | TMS | Feb'26 | On going
54 | DOTMS | STPIM | Feb'26 | On going
55 | Blockchain | STPIM | Feb'26 | #REF!
56 | HEX | P2P | Feb'26 | #REF!
57 | HEX | STPIM | Feb'26 | #REF!
58 | HEX | OTB | Feb'26 | #REF!
59 | HEX | Fin & Accn | Feb'26 | Not started
60 | HEX | EDM | Feb'26 | Not started
61 | BSC | N/A | Feb'26
62 | eBAPA | Estate Operation | Feb'26 | #REF! | Will not be in current eBAPA scope
63 | Estate master data hierarchy | Estate Operation | Feb'26 | On going
64 | Estate operational metric | Estate Operation | Feb'26 | On going
65 | LIS | P2P | Feb'26 | On going
66 | LIS | Trading | Feb'26 | Not started
67 | WB DS | TMS | Feb'26 | Not started
68 | WB DS | Trading | Feb'26 | Not started
69 | WB DS | STPIM | Feb'26 | On going
70 | WB DS | EDM | Feb'26 | Not started
71 | WB oleo/socimas | TMS | Feb'26 | Not started
72 | WB oleo/socimas | Trading | Feb'26 | Not started
73 | WB oleo/socimas | STPIM | Feb'26 | Not started
74 | WB oleo/socimas | EDM | Feb'26 | Not started
75 | Quality Window | P2P | Feb'26 | Not started
76 | Quality Window | Trading | Feb'26 | Not started
77 | e-BAST | Asset Maintenance | Feb'26 | On going
78 | e-BAST | P2P | Feb'26 | #REF!
79 | e-BAST | TMS | Feb'26 | Not started
80 | e-BAST | STPIM | Feb'26 | On going
81 | e-BAST | OTB | Feb'26 | Completed
82 | COPS | TMS | Feb'26 | On going
83 | COPS | Trading | Feb'26 | Not started
84 | JIMS | TMS | Feb'26 | On going
85 | JIMS | Trading | Feb'26 | Not started
86 | MIGLI | Asset Maintenance | Feb'26 | #REF!
87 | MIGLI | TMS | Feb'26 | Not started
88 | CILT | Asset Maintenance | Feb'26 | #REF!
89 | BASYS | STPIM | Feb'26 | On going
90 | ASRS (vendor) | STPIM | Feb'26 | Not started
91 | ePO | STPIM | Feb'26 | Not started
92 | SmartTrace | STPIM | Feb'26 | Not started
93 | Mass Balance | STPIM | Feb'26 | Not started
94 | Vendor evaluation | STPIM | Feb'26 | Not started
95 | DAMIMAS | OTB | Feb'26 | Not started
96 | Doc tracking | OTB | Feb'26 | Completed
97 | LC | Fin & Accn | Feb'26 | Not started
98 | PL overview | Fin & Accn | Feb'26 | On going
99 | DiFi | Fin & Accn | Feb'26 | On going
100 | Supplier financing | Fin & Accn | Feb'26 | On going
101 | Asset handheld | Fin & Accn | Feb'26 | On going
102 | FR automation | Fin & Accn | Feb'26 | On going
103 | Coretax | Fin & Accn | Feb'26 | On going
104 | eBanking | Fin & Accn | Feb'26 | On going
105 | Tungsten | Fin & Accn | Feb'26 | On going
106 | CRQ | EDM | Feb'26 | Not started
107 | PTA approval |  | Feb'26
108 | SPK form |  | Feb'26
109 | MDG |  | Feb'26
110 | GRC |  | Feb'26
111 | AIMS | Asset Maintenance | Feb'26 | #REF!
Note :
P2P kurang eBAST
Trading kurang WB downstream and Socimas
STPIM kurang BPC
OTB kurang eBAST
Note on E96: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Jason Andrew Hardjawidjaja (Ext) please double check status, not aligned with tab TMS
Note on A131: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Jason Andrew Hardjawidjaja (Ext) please check again

## 2. Discussion new integration (hidden)
# | Application Name | Stream | When | Status | Remarks
1 | Remedy/Helix, KUBE | Asset Maintenance | Feb'26 | On going
2 | Remedy/Helix, KUBE | STPIM | Feb'26 | 0
3 | Remedy/Helix, KUBE | OTB | Feb'26 | Completed
4 | Remedy/Helix, KUBE | Fin & Accn | Feb'26 | On going
5 | Remedy/Helix, KUBE | EDM | Feb'26 | 0
6 | Coupa | TMS | Feb'26 | 0
7 | Coupa | STPIM | Feb'26 | On going
8 | Coupa | OTB | Feb'26 | #REF!
9 | Coupa | EDM | Feb'26 | 0
10 | eFACT | Estate Operation | Feb'26 | On going
11 | eFACT | P2P | Feb'26 | On going
12 | eFACT | STPIM | Feb'26 | 0
13 | eFACT | Fin & Accn | Feb'26 | 0
14 | MES | Asset Maintenance | Feb'26 | #REF!
15 | MES | P2P | Feb'26 | Completed
16 | ProInt | Fin & Accn | Feb'26 | On going
17 | New Checkroll | Estate Operation | Feb'26 | On going
18 | New Checkroll | TMS | Feb'26 | 0
19 | New Checkroll | STPIM | Feb'26 | 0
20 | New Checkroll | Fin & Accn | Feb'26 | On going
21 | New Checkroll | EDM | Feb'26 | 0
22 | WB US | Estate Operation | Feb'26 | 0
23 | WB US | TMS | Feb'26 | 0
24 | WB US | Trading | Feb'26 | 0
25 | WB US | STPIM | Feb'26 | 0
26 | WB US | OTB | Feb'26 | Completed
27 | WB US | EDM | Feb'26 | 0
28 | SMART WB | TMS | Feb'26 | 0
29 | SMART WB | Trading | Feb'26 | 0
30 | LIMS | P2P | Feb'26 | On going
31 | LIMS | Trading | Feb'26 | 0
32 | iLogs (vendor) | TMS | Feb'26 | 0
33 | iLogs (vendor) | Trading | Feb'26 | 0
34 | iLogs (vendor) | STPIM | Feb'26 | 0
35 | iLogs (vendor) | OTB | Feb'26 | Completed
36 | Workday | Fin & Accn | Feb'26 | On going
37 | Workday | EDM | Feb'26 | 0
38 | Esker | N/A | Feb'26
39 | Agiblock | N/A | Feb'26
40 | IDSP/IOM | P2P | Feb'26 | Completed
41 | IDSP/IOM | OTB | Feb'26 | Not started
42 | Dashboard (Power BI / DOMO etc.) | All Streams | Feb'26
43 | BPC | Estate Operation | Feb'26 | On going
44 | BPC | STPIM | Feb'26 | 0
45 | BPC | Fin & Accn | Feb'26 | 0
46 | BW | P2P | Feb'26 | #REF!
47 | BW | STPIM | Feb'26 | 0
48 | BW | Fin & Accn | Feb'26 | 0
49 | BW | OTB | Feb'26 | #REF!
50 | BW | EDM | Feb'26 | 0
51 | DOTMS | Estate Operation | Feb'26 | #REF!
52 | DOTMS | Asset Maintenance | Feb'26 | On going
53 | DOTMS | TMS | Feb'26 | On going
54 | DOTMS | STPIM | Feb'26 | 0
55 | Blockchain | STPIM | Feb'26 | #REF!
56 | HEX | P2P | Feb'26 | #REF!
57 | HEX | STPIM | Feb'26 | #REF!
58 | HEX | OTB | Feb'26 | #REF!
59 | HEX | Fin & Accn | Feb'26 | 0
60 | HEX | EDM | Feb'26 | 0
61 | BSC | N/A | Feb'26
62 | eBAPA | Estate Operation | Feb'26 | #REF!
63 | Estate master data hierarchy | Estate Operation | Feb'26 | 0
64 | Estate operational metric | Estate Operation | Feb'26 | 0
65 | LIS | P2P | Feb'26 | Completed
66 | LIS | Trading | Feb'26 | 0
67 | WB DS | TMS | Feb'26 | 0
68 | WB DS | Trading | Feb'26 | 0
69 | WB DS | STPIM | Feb'26 | 0
70 | WB DS | EDM | Feb'26 | 0
71 | WB oleo/socimas | TMS | Feb'26 | 0
72 | WB oleo/socimas | Trading | Feb'26 | 0
73 | WB oleo/socimas | STPIM | Feb'26 | 0
74 | WB oleo/socimas | EDM | Feb'26 | 0
75 | Quality Window | P2P | Feb'26 | Not started
76 | Quality Window | Trading | Feb'26 | 0
77 | e-BAST | Asset Maintenance | Feb'26 | On going
78 | e-BAST | P2P | Feb'26 | #REF!
79 | e-BAST | TMS | Feb'26 | 0
80 | e-BAST | STPIM | Feb'26 | 0
81 | e-BAST | OTB | Feb'26 | Completed
82 | COPS | TMS | Feb'26 | 0
83 | COPS | Trading | Feb'26 | 0
84 | JIMS | TMS | Feb'26 | 0
85 | JIMS | Trading | Feb'26 | 0
86 | MIGLI | Asset Maintenance | Feb'26 | #REF!
87 | MIGLI | TMS | Feb'26 | 0
88 | CILT | Asset Maintenance | Feb'26 | #REF!
89 | BASYS | STPIM | Feb'26 | 0
90 | ASRS (vendor) | STPIM | Feb'26 | 0
91 | ePO | STPIM | Feb'26 | 0
92 | SmartTrace | STPIM | Feb'26 | 0
93 | Mass Balance | STPIM | Feb'26 | 0
94 | Vendor evaluation | STPIM | Feb'26 | 0
95 | DAMIMAS | OTB | Feb'26 | Completed
96 | Doc tracking | OTB | Feb'26 | Completed
97 | LC | Fin & Accn | Feb'26 | 0
98 | PL overview | Fin & Accn | Feb'26 | On going
99 | DiFi | Fin & Accn | Feb'26 | On going
100 | Supplier financing | Fin & Accn | Feb'26 | On going
101 | Asset handheld | Fin & Accn | Feb'26 | On going
102 | FR automation | Fin & Accn | Feb'26 | On going
103 | Coretax | Fin & Accn | Feb'26 | On going
104 | eBanking | Fin & Accn | Feb'26 | On going
105 | Tungsten | Fin & Accn | Feb'26 | On going
106 | CRQ | EDM | Feb'26 | 0
107 | PTA approval |  | Feb'26
108 | SPK form |  | Feb'26
109 | MDG |  | Feb'26
110 | GRC |  | Feb'26
111 | AIMS | Asset Maintenance | Feb'26 | #REF!

## 5. Application change require (hidden)
# | Application Name | Stream | When | Status | Remarks
1 | Remedy/Helix, KUBE | Asset Maintenance | Feb'26 | 0
2 | Remedy/Helix, KUBE | STPIM | Feb'26 | 0
3 | Remedy/Helix, KUBE | OTB | Feb'26 | 0
4 | Remedy/Helix, KUBE | Fin & Accn | Feb'26 | On going
5 | Remedy/Helix, KUBE | EDM | Feb'26 | 0
6 | Coupa | TMS | Feb'26 | 0
7 | Coupa | STPIM | Feb'26 | On going
8 | Coupa | OTB | Feb'26 | #REF!
9 | Coupa | EDM | Feb'26 | 0
10 | eFACT | Estate Operation | Feb'26 | 0
11 | eFACT | P2P | Feb'26 | 0
12 | eFACT | STPIM | Feb'26 | 0
13 | eFACT | Fin & Accn | Feb'26 | 0
14 | MES | Asset Maintenance | Feb'26 | #REF!
15 | MES | P2P | Feb'26 | 0
16 | ProInt | Fin & Accn | Feb'26 | On going
17 | New Checkroll | Estate Operation | Feb'26 | 0
18 | New Checkroll | TMS | Feb'26 | 0
19 | New Checkroll | STPIM | Feb'26 | 0
20 | New Checkroll | Fin & Accn | Feb'26 | On going
21 | New Checkroll | EDM | Feb'26 | 0
22 | WB US | Estate Operation | Feb'26 | 0
23 | WB US | TMS | Feb'26 | 0
24 | WB US | Trading | Feb'26 | 0
25 | WB US | STPIM | Feb'26 | 0
26 | WB US | OTB | Feb'26 | 0
27 | WB US | EDM | Feb'26 | 0
28 | SMART WB | TMS | Feb'26 | 0
29 | SMART WB | Trading | Feb'26 | 0
30 | LIMS | P2P | Feb'26 | 0
31 | LIMS | Trading | Feb'26 | 0
32 | iLogs (vendor) | TMS | Feb'26 | 0
33 | iLogs (vendor) | Trading | Feb'26 | 0
34 | iLogs (vendor) | STPIM | Feb'26 | 0
35 | iLogs (vendor) | OTB | Feb'26 | 0
36 | Workday | Fin & Accn | Feb'26 | On going
37 | Workday | EDM | Feb'26 | 0
38 | Esker | N/A | Feb'26
39 | Agiblock | N/A | Feb'26
40 | IDSP/IOM | P2P | Feb'26 | 0
41 | IDSP/IOM | OTB | Feb'26 | 0
42 | Dashboard (Power BI / DOMO etc.) | All Streams | Feb'26
43 | BPC | Estate Operation | Feb'26 | 0
44 | BPC | STPIM | Feb'26 | 0
45 | BPC | Fin & Accn | Feb'26 | 0
46 | BW | P2P | Feb'26 | #REF!
47 | BW | STPIM | Feb'26 | 0
48 | BW | Fin & Accn | Feb'26 | 0
49 | BW | OTB | Feb'26 | #REF!
50 | BW | EDM | Feb'26 | 0
51 | DOTMS | Estate Operation | Feb'26 | #REF!
52 | DOTMS | Asset Maintenance | Feb'26 | On going
53 | DOTMS | TMS | Feb'26 | On going
54 | DOTMS | STPIM | Feb'26 | 0
55 | Blockchain | STPIM | Feb'26 | #REF!
56 | HEX | P2P | Feb'26 | #REF!
57 | HEX | STPIM | Feb'26 | #REF!
58 | HEX | OTB | Feb'26 | #REF!
59 | HEX | Fin & Accn | Feb'26 | 0
60 | HEX | EDM | Feb'26 | 0
61 | BSC | N/A | Feb'26
62 | eBAPA | Estate Operation | Feb'26 | #REF!
63 | Estate master data hierarchy | Estate Operation | Feb'26 | 0
64 | Estate operational metric | Estate Operation | Feb'26 | 0
65 | LIS | P2P | Feb'26 | Not started
66 | LIS | Trading | Feb'26 | Not started
67 | WB DS | TMS | Feb'26 | 0
68 | WB DS | Trading | Feb'26 | Not started
69 | WB DS | STPIM | Feb'26 | 0
70 | WB DS | EDM | Feb'26 | 0
71 | WB oleo/socimas | TMS | Feb'26 | 0
72 | WB oleo/socimas | Trading | Feb'26 | Not started
73 | WB oleo/socimas | STPIM | Feb'26 | 0
74 | WB oleo/socimas | EDM | Feb'26 | 0
75 | Quality Window | P2P | Feb'26 | 0
76 | Quality Window | Trading | Feb'26 | 0
77 | e-BAST | Asset Maintenance | Feb'26 | On going
78 | e-BAST | P2P | Feb'26 | #REF!
79 | e-BAST | TMS | Feb'26 | 0
80 | e-BAST | STPIM | Feb'26 | 0
81 | e-BAST | OTB | Feb'26 | 0
82 | COPS | TMS | Feb'26 | 0
83 | COPS | Trading | Feb'26 | 0
84 | JIMS | TMS | Feb'26 | 0
85 | JIMS | Trading | Feb'26 | 0
86 | MIGLI | Asset Maintenance | Feb'26 | #REF!
87 | MIGLI | TMS | Feb'26 | 0
88 | CILT | Asset Maintenance | Feb'26 | #REF!
89 | BASYS | STPIM | Feb'26 | On going
90 | ASRS (vendor) | STPIM | Feb'26 | 0
91 | ePO | STPIM | Feb'26 | 0
92 | SmartTrace | STPIM | Feb'26 | 0
93 | Mass Balance | STPIM | Feb'26 | 0
94 | Vendor evaluation | STPIM | Feb'26 | 0
95 | DAMIMAS | OTB | Feb'26 | Not started
96 | Doc tracking | OTB | Feb'26 | Not started
97 | LC | Fin & Accn | Feb'26 | 0
98 | PL overview | Fin & Accn | Feb'26 | On going
99 | DiFi | Fin & Accn | Feb'26 | On going
100 | Supplier financing | Fin & Accn | Feb'26 | On going
101 | Asset handheld | Fin & Accn | Feb'26 | On going
102 | FR automation | Fin & Accn | Feb'26 | On going
103 | Coretax | Fin & Accn | Feb'26 | On going
104 | eBanking | Fin & Accn | Feb'26 | On going
105 | Tungsten | Fin & Accn | Feb'26 | On going
106 | CRQ | EDM | Feb'26 | 0
107 | PTA approval |  | Feb'26
108 | SPK form |  | Feb'26
109 | MDG |  | Feb'26
110 | GRC |  | Feb'26
111 | AIMS | Asset Maintenance | Feb'26 | #REF!

## 6. Discuss rollout readiness (hidden)
# | Application Name | Stream | When | Status | Remarks
1 | Remedy/Helix, KUBE | Asset Maintenance | Feb'26 | 0
2 | Remedy/Helix, KUBE | STPIM | Feb'26 | 0
3 | Remedy/Helix, KUBE | OTB | Feb'26 | 0
4 | Remedy/Helix, KUBE | Fin & Accn | Feb'26 | On going
5 | Remedy/Helix, KUBE | EDM | Feb'26 | 0
6 | Coupa | TMS | Feb'26 | 0
7 | Coupa | STPIM | Feb'26 | 0
8 | Coupa | OTB | Feb'26 | #REF!
9 | Coupa | EDM | Feb'26 | 0
10 | eFACT | Estate Operation | Feb'26 | 0
11 | eFACT | P2P | Feb'26 | 0
12 | eFACT | STPIM | Feb'26 | 0
13 | eFACT | Fin & Accn | Feb'26 | 0
14 | MES | Asset Maintenance | Feb'26 | #REF!
15 | MES | P2P | Feb'26 | 0
16 | ProInt | Fin & Accn | Feb'26 | On going
17 | New Checkroll | Estate Operation | Feb'26 | 0
18 | New Checkroll | TMS | Feb'26 | 0
19 | New Checkroll | STPIM | Feb'26 | 0
20 | New Checkroll | Fin & Accn | Feb'26 | On going
21 | New Checkroll | EDM | Feb'26 | 0
22 | WB US | Estate Operation | Feb'26 | 0
23 | WB US | TMS | Feb'26 | 0
24 | WB US | Trading | Feb'26 | 0
25 | WB US | STPIM | Feb'26 | 0
26 | WB US | OTB | Feb'26 | 0
27 | WB US | EDM | Feb'26 | 0
28 | SMART WB | TMS | Feb'26 | 0
29 | SMART WB | Trading | Feb'26 | 0
30 | LIMS | P2P | Feb'26 | 0
31 | LIMS | Trading | Feb'26 | 0
32 | iLogs (vendor) | TMS | Feb'26 | 0
33 | iLogs (vendor) | Trading | Feb'26 | 0
34 | iLogs (vendor) | STPIM | Feb'26 | 0
35 | iLogs (vendor) | OTB | Feb'26 | 0
36 | Workday | Fin & Accn | Feb'26 | On going
37 | Workday | EDM | Feb'26 | 0
38 | Esker | N/A | Feb'26
39 | Agiblock | N/A | Feb'26
40 | IDSP/IOM | P2P | Feb'26 | 0
41 | IDSP/IOM | OTB | Feb'26 | 0
42 | Dashboard (Power BI / DOMO etc.) | All Streams | Feb'26
43 | BPC | Estate Operation | Feb'26 | 0
44 | BPC | STPIM | Feb'27 | 0
45 | BPC | Fin & Accn | Feb'26 | 0
46 | BW | P2P | Feb'26 | #REF!
47 | BW | STPIM | Feb'26 | 0
48 | BW | Fin & Accn | Feb'26 | 0
49 | BW | OTB | Feb'26 | #REF!
50 | BW | EDM | Feb'26 | 0
51 | DOTMS | Estate Operation | Feb'26 | #REF!
52 | DOTMS | Asset Maintenance | Feb'26 | 0
53 | DOTMS | TMS | Feb'26 | 0
54 | DOTMS | STPIM | Feb'26 | 0
55 | Blockchain | STPIM | Feb'26 | #REF!
56 | HEX | P2P | Feb'26 | #REF!
57 | HEX | STPIM | Feb'26 | #REF!
58 | HEX | OTB | Feb'26 | #REF!
59 | HEX | Fin & Accn | Feb'26 | 0
60 | HEX | EDM | Feb'26 | 0
61 | BSC | N/A | Feb'26
62 | eBAPA | Estate Operation | Feb'26 | #REF!
63 | Estate master data hierarchy | Estate Operation | Feb'26 | 0
64 | Estate operational metric | Estate Operation | Feb'26 | 0
65 | LIS | P2P | Feb'26 | Not started
66 | LIS | Trading | Feb'26 | Not started
67 | WB DS | TMS | Feb'26 | 0
68 | WB DS | Trading | Feb'26 | Not started
69 | WB DS | STPIM | Feb'26 | 0
70 | WB DS | EDM | Feb'26 | 0
71 | WB oleo/socimas | TMS | Feb'26 | 0
72 | WB oleo/socimas | Trading | Feb'26 | Not started
73 | WB oleo/socimas | STPIM | Feb'26 | 0
74 | WB oleo/socimas | EDM | Feb'26 | 0
75 | Quality Window | P2P | Feb'26 | 0
76 | Quality Window | Trading | Feb'26 | 0
77 | e-BAST | Asset Maintenance | Feb'26 | On going
78 | e-BAST | P2P | Feb'26 | #REF!
79 | e-BAST | TMS | Feb'26 | 0
80 | e-BAST | STPIM | Feb'26 | 0
81 | e-BAST | OTB | Feb'26 | Completed
82 | COPS | TMS | Feb'26 | 0
83 | COPS | Trading | Feb'26 | 0
84 | JIMS | TMS | Feb'26 | 0
85 | JIMS | Trading | Feb'26 | 0
86 | MIGLI | Asset Maintenance | Feb'26 | #REF!
87 | MIGLI | TMS | Feb'26 | 0
88 | CILT | Asset Maintenance | Feb'26 | #REF!
89 | BASYS | STPIM | Feb'26 | Not started
90 | ASRS (vendor) | STPIM | Feb'26 | 0
91 | ePO | STPIM | Feb'26 | 0
92 | SmartTrace | STPIM | Feb'26 | 0
93 | Mass Balance | STPIM | Feb'26 | 0
94 | Vendor evaluation | STPIM | Feb'26 | 0
95 | DAMIMAS | OTB | Feb'26 | Not started
96 | Doc tracking | OTB | Feb'26 | 0
97 | LC | Fin & Accn | Feb'26 | 0
98 | PL overview | Fin & Accn | Feb'26 | On going
99 | DiFi | Fin & Accn | Feb'26 | On going
100 | Supplier financing | Fin & Accn | Feb'26 | On going
101 | Asset handheld | Fin & Accn | Feb'26 | On going
102 | FR automation | Fin & Accn | Feb'26 | On going
103 | Coretax | Fin & Accn | Feb'26 | On going
104 | eBanking | Fin & Accn | Feb'26 | On going
105 | Tungsten | Fin & Accn | Feb'26 | On going
106 | CRQ | EDM | Feb'26 | 0
107 | PTA approval |  | Feb'26
108 | SPK form |  | Feb'26
109 | MDG |  | Feb'26
110 | GRC |  | Feb'26
111 | AIMS | Asset Maintenance | Feb'26 | #REF!

## 7. Project Timeline (hidden)
# | Application Name | Stream | When | Status | Remarks
1 | Remedy/Helix, KUBE | Asset Maintenance | Mar'26 | 0
2 | Remedy/Helix, KUBE | STPIM | Mar'26 | 0
3 | Remedy/Helix, KUBE | OTB | Mar'26 | 0
4 | Remedy/Helix, KUBE | Fin & Accn | Mar'26 | 0
5 | Remedy/Helix, KUBE | EDM | Mar'26 | 0
6 | Coupa | TMS | Mar'26 | 0
7 | Coupa | STPIM | Mar'26 | On going
8 | Coupa | OTB | Mar'26 | #REF!
9 | Coupa | EDM | Mar'26 | 0
10 | eFACT | Estate Operation | Mar'26 | 0
11 | eFACT | P2P | Mar'26 | 0
12 | eFACT | STPIM | Mar'26 | 0
13 | eFACT | Fin & Accn | Mar'26 | 0
14 | MES | Asset Maintenance | Mar'26 | #REF!
15 | MES | P2P | Mar'26 | 0
16 | ProInt | Fin & Accn | Mar'26 | 0
17 | New Checkroll | Estate Operation | Mar'26 | 0
18 | New Checkroll | TMS | Mar'26 | 0
19 | New Checkroll | STPIM | Mar'26 | 0
20 | New Checkroll | Fin & Accn | Mar'26 | 0
21 | New Checkroll | EDM | Mar'26 | 0
22 | WB US | Estate Operation | Mar'26 | 0
23 | WB US | TMS | Mar'26 | 0
24 | WB US | Trading | Mar'26 | 0
25 | WB US | STPIM | Mar'26 | 0
26 | WB US | OTB | Mar'26 | 0
27 | WB US | EDM | Mar'26 | 0
28 | SMART WB | TMS | Mar'26 | 0
29 | SMART WB | Trading | Mar'26 | 0
30 | LIMS | P2P | Mar'26 | 0
31 | LIMS | Trading | Mar'26 | 0
32 | iLogs (vendor) | TMS | Mar'26 | 0
33 | iLogs (vendor) | Trading | Mar'26 | 0
34 | iLogs (vendor) | STPIM | Mar'26 | 0
35 | iLogs (vendor) | OTB | Mar'26 | 0
36 | Workday | Fin & Accn | Mar'26 | 0
37 | Workday | EDM | Mar'26 | 0
38 | Esker | N/A | Mar'26
39 | Agiblock | N/A | Mar'26
40 | IDSP/IOM | P2P | Mar'26 | 0
41 | IDSP/IOM | OTB | Mar'26 | 0
42 | Dashboard (Power BI / DOMO etc.) | All Streams | Mar'26
43 | BPC | Estate Operation | Mar'26 | 0
44 | BPC | STPIM | Mar'26 | 0
45 | BPC | Fin & Accn | Mar'26 | 0
46 | BW | P2P | Mar'26 | #REF!
47 | BW | STPIM | Mar'26 | 0
48 | BW | Fin & Accn | Mar'26 | 0
49 | BW | OTB | Mar'26 | #REF!
50 | BW | EDM | Mar'26 | 0
51 | DOTMS | Estate Operation | Mar'26 | #REF!
52 | DOTMS | Asset Maintenance | Mar'26 | 0
53 | DOTMS | TMS | Mar'26 | 0
54 | DOTMS | STPIM | Mar'26 | 0
55 | Blockchain | STPIM | Mar'26 | #REF!
56 | HEX | P2P | Mar'26 | #REF!
57 | HEX | STPIM | Mar'26 | #REF!
58 | HEX | OTB | Mar'26 | #REF!
59 | HEX | Fin & Accn | Mar'26 | 0
60 | HEX | EDM | Mar'26 | 0
61 | BSC | N/A | Mar'26
62 | eBAPA | Estate Operation | Mar'26 | #REF!
63 | Estate master data hierarchy | Estate Operation | Mar'26 | 0
64 | Estate operational metric | Estate Operation | Mar'26 | 0
65 | LIS | P2P | Mar'26 | On going
66 | LIS | Trading | Mar'26 | On going
67 | WB DS | TMS | Mar'26 | 0
68 | WB DS | Trading | Mar'26 | Not started
69 | WB DS | STPIM | Mar'26 | 0
70 | WB DS | EDM | Mar'26 | 0
71 | WB oleo/socimas | TMS | Mar'26 | 0
72 | WB oleo/socimas | Trading | Mar'26 | Not started
73 | WB oleo/socimas | STPIM | Mar'26 | 0
74 | WB oleo/socimas | EDM | Mar'26 | 0
75 | Quality Window | P2P | Mar'26 | 0
76 | Quality Window | Trading | Mar'26 | 0
77 | e-BAST | Asset Maintenance | Mar'26 | Not started
78 | e-BAST | P2P | Mar'26 | #REF!
79 | e-BAST | TMS | Mar'26 | 0
80 | e-BAST | STPIM | Mar'26 | 0
81 | e-BAST | OTB | Mar'26 | 0
82 | COPS | TMS | Mar'26 | 0
83 | COPS | Trading | Mar'26 | 0
84 | JIMS | TMS | Mar'26 | 0
85 | JIMS | Trading | Mar'26 | 0
86 | MIGLI | Asset Maintenance | Mar'26 | #REF!
87 | MIGLI | TMS | Mar'26 | 0
88 | CILT | Asset Maintenance | Mar'26 | #REF!
89 | BASYS | STPIM | Mar'26 | Not started
90 | ASRS (vendor) | STPIM | Mar'26 | 0
91 | ePO | STPIM | Mar'26 | 0
92 | SmartTrace | STPIM | Mar'26 | 0
93 | Mass Balance | STPIM | Mar'26 | 0
94 | Vendor evaluation | STPIM | Mar'26 | 0
95 | DAMIMAS | OTB | Mar'26 | Not started
96 | Doc tracking | OTB | Mar'26 | 0
97 | LC | Fin & Accn | Mar'26 | 0
98 | PL overview | Fin & Accn | Mar'26 | 0
99 | DiFi | Fin & Accn | Mar'26 | 0
100 | Supplier financing | Fin & Accn | Mar'26 | 0
101 | Asset handheld | Fin & Accn | Mar'26 | 0
102 | FR automation | Fin & Accn | Mar'26 | 0
103 | Coretax | Fin & Accn | Mar'26 | 0
104 | eBanking | Fin & Accn | Mar'26 | 0
105 | Tungsten | Fin & Accn | Mar'26 | 0
106 | CRQ | EDM | Mar'26 | 0
107 | PTA approval |  | Mar'26
108 | SPK form |  | Mar'26
109 | MDG |  | Mar'26
110 | GRC |  | Mar'26
111 | AIMS | Asset Maintenance | Mar'26 | #REF!

## 9. Prioritization of Build (hidden)
# | Application Name | Stream | When | Status | Remarks
1 | Remedy/Helix, KUBE | Asset Maintenance | Mar'26 | 0
2 | Remedy/Helix, KUBE | STPIM | Mar'26 | 0
3 | Remedy/Helix, KUBE | OTB | Mar'26 | 0
4 | Remedy/Helix, KUBE | Fin & Accn | Mar'26 | 0
5 | Remedy/Helix, KUBE | EDM | Mar'26 | 0
6 | Coupa | TMS | Mar'26 | 0
7 | Coupa | STPIM | Mar'26 | On going
8 | Coupa | OTB | Mar'26 | #REF!
9 | Coupa | EDM | Mar'26 | 0
10 | eFACT | Estate Operation | Mar'26 | 0
11 | eFACT | P2P | Mar'26 | 0
12 | eFACT | STPIM | Mar'26 | 0
13 | eFACT | Fin & Accn | Mar'26 | 0
14 | MES | Asset Maintenance | Mar'26 | #REF!
15 | MES | P2P | Mar'26 | 0
16 | ProInt | Fin & Accn | Mar'26 | 0
17 | New Checkroll | Estate Operation | Mar'26 | 0
18 | New Checkroll | TMS | Mar'26 | 0
19 | New Checkroll | STPIM | Mar'26 | 0
20 | New Checkroll | Fin & Accn | Mar'26 | 0
21 | New Checkroll | EDM | Mar'26 | 0
22 | WB US | Estate Operation | Mar'26 | 0
23 | WB US | TMS | Mar'26 | 0
24 | WB US | Trading | Mar'26 | 0
25 | WB US | STPIM | Mar'26 | 0
26 | WB US | OTB | Mar'26 | 0
27 | WB US | EDM | Mar'26 | 0
28 | SMART WB | TMS | Mar'26 | 0
29 | SMART WB | Trading | Mar'26 | 0
30 | LIMS | P2P | Mar'26 | 0
31 | LIMS | Trading | Mar'26 | 0
32 | iLogs (vendor) | TMS | Mar'26 | 0
33 | iLogs (vendor) | Trading | Mar'26 | 0
34 | iLogs (vendor) | STPIM | Mar'26 | 0
35 | iLogs (vendor) | OTB | Mar'26 | 0
36 | Workday | Fin & Accn | Mar'26 | 0
37 | Workday | EDM | Mar'26 | 0
38 | Esker | N/A | Mar'26
39 | Agiblock | N/A | Mar'26
40 | IDSP/IOM | P2P | Mar'26 | 0
41 | IDSP/IOM | OTB | Mar'26 | 0
42 | Dashboard (Power BI / DOMO etc.) | All Streams | Mar'26
43 | BPC | Estate Operation | Mar'26 | 0
44 | BPC | STPIM | Mar'26 | 0
45 | BPC | Fin & Accn | Mar'26 | 0
46 | BW | P2P | Mar'26 | #REF!
47 | BW | STPIM | Mar'26 | 0
48 | BW | Fin & Accn | Mar'26 | 0
49 | BW | OTB | Mar'26 | #REF!
50 | BW | EDM | Mar'26 | 0
51 | DOTMS | Estate Operation | Mar'26 | #REF!
52 | DOTMS | Asset Maintenance | Mar'26 | 0
53 | DOTMS | TMS | Mar'26 | 0
54 | DOTMS | STPIM | Mar'26 | 0
55 | Blockchain | STPIM | Mar'26 | #REF!
56 | HEX | P2P | Mar'26 | #REF!
57 | HEX | STPIM | Mar'26 | #REF!
58 | HEX | OTB | Mar'26 | #REF!
59 | HEX | Fin & Accn | Mar'26 | 0
60 | HEX | EDM | Mar'26 | 0
61 | BSC | N/A | Mar'26
62 | eBAPA | Estate Operation | Mar'26 | #REF!
63 | Estate master data hierarchy | Estate Operation | Mar'26 | 0
64 | Estate operational metric | Estate Operation | Mar'26 | 0
65 | LIS | P2P | Mar'26 | 0
66 | LIS | Trading | Mar'26 | 0
67 | WB DS | TMS | Mar'26 | 0
68 | WB DS | Trading | Mar'26 | 0
69 | WB DS | STPIM | Mar'26 | 0
70 | WB DS | EDM | Mar'26 | 0
71 | WB oleo/socimas | TMS | Mar'26 | 0
72 | WB oleo/socimas | Trading | Mar'26 | 0
73 | WB oleo/socimas | STPIM | Mar'26 | 0
74 | WB oleo/socimas | EDM | Mar'26 | 0
75 | Quality Window | P2P | Mar'26 | 0
76 | Quality Window | Trading | Mar'26 | 0
77 | e-BAST | Asset Maintenance | Mar'26 | 0
78 | e-BAST | P2P | Mar'26 | #REF!
79 | e-BAST | TMS | Mar'26 | 0
80 | e-BAST | STPIM | Mar'26 | 0
81 | e-BAST | OTB | Mar'26 | 0
82 | COPS | TMS | Mar'26 | 0
83 | COPS | Trading | Mar'26 | 0
84 | JIMS | TMS | Mar'26 | 0
85 | JIMS | Trading | Mar'26 | 0
86 | MIGLI | Asset Maintenance | Mar'26 | #REF!
87 | MIGLI | TMS | Mar'26 | 0
88 | CILT | Asset Maintenance | Mar'26 | #REF!
89 | BASYS | STPIM | Mar'26 | 0
90 | ASRS (vendor) | STPIM | Mar'26 | 0
91 | ePO | STPIM | Mar'26 | 0
92 | SmartTrace | STPIM | Mar'26 | 0
93 | Mass Balance | STPIM | Mar'26 | 0
94 | Vendor evaluation | STPIM | Mar'26 | 0
95 | DAMIMAS | OTB | Mar'26 | 0
96 | Doc tracking | OTB | Mar'26 | 0
97 | LC | Fin & Accn | Mar'26 | 0
98 | PL overview | Fin & Accn | Mar'26 | 0
99 | DiFi | Fin & Accn | Mar'26 | 0
100 | Supplier financing | Fin & Accn | Mar'26 | 0
101 | Asset handheld | Fin & Accn | Mar'26 | 0
102 | FR automation | Fin & Accn | Mar'26 | 0
103 | Coretax | Fin & Accn | Mar'26 | 0
104 | eBanking | Fin & Accn | Mar'26 | 0
105 | Tungsten | Fin & Accn | Mar'26 | 0
106 | CRQ | EDM | Mar'26 | 0
107 | PTA approval |  | Mar'26
108 | SPK form |  | Mar'26
109 | MDG |  | Mar'26
110 | GRC |  | Mar'26
111 | AIMS | Asset Maintenance | Mar'26 | #REF!

## 10. Solution Migration (hidden)
# | Application Name | Stream | When | Status | Remarks
1 | Remedy/Helix, KUBE | Asset Maintenance | Apr'26 | 0
2 | Remedy/Helix, KUBE | STPIM | Apr'26 | 0
3 | Remedy/Helix, KUBE | OTB | Apr'26 | 0
4 | Remedy/Helix, KUBE | Fin & Accn | Apr'26 | 0
5 | Remedy/Helix, KUBE | EDM | Apr'26 | 0
6 | Coupa | TMS | Apr'26 | 0
7 | Coupa | STPIM | Apr'26 | 0
8 | Coupa | OTB | Apr'26 | #REF!
9 | Coupa | EDM | Apr'26 | 0
10 | eFACT | Estate Operation | Apr'26 | 0
11 | eFACT | P2P | Apr'26 | 0
12 | eFACT | STPIM | Apr'26 | 0
13 | eFACT | Fin & Accn | Apr'26 | 0
14 | MES | Asset Maintenance | Apr'26 | #REF!
15 | MES | P2P | Apr'26 | 0
16 | ProInt | Fin & Accn | Apr'26 | 0
17 | New Checkroll | Estate Operation | Apr'26 | 0
18 | New Checkroll | TMS | Apr'26 | 0
19 | New Checkroll | STPIM | Apr'26 | 0
20 | New Checkroll | Fin & Accn | Apr'26 | 0
21 | New Checkroll | EDM | Apr'26 | 0
22 | WB US | Estate Operation | Apr'26 | 0
23 | WB US | TMS | Apr'26 | 0
24 | WB US | Trading | Apr'26 | 0
25 | WB US | STPIM | Apr'26 | 0
26 | WB US | OTB | Apr'26 | 0
27 | WB US | EDM | Apr'26 | 0
28 | SMART WB | TMS | Apr'26 | 0
29 | SMART WB | Trading | Apr'26 | 0
30 | LIMS | P2P | Apr'26 | 0
31 | LIMS | Trading | Apr'26 | 0
32 | iLogs (vendor) | TMS | Apr'26 | 0
33 | iLogs (vendor) | Trading | Apr'26 | 0
34 | iLogs (vendor) | STPIM | Apr'26 | 0
35 | iLogs (vendor) | OTB | Apr'26 | 0
36 | Workday | Fin & Accn | Apr'26 | 0
37 | Workday | EDM | Apr'26 | 0
38 | Esker | N/A | Apr'26
39 | Agiblock | N/A | Apr'26
40 | IDSP/IOM | P2P | Apr'26 | 0
41 | IDSP/IOM | OTB | Apr'26 | 0
42 | Dashboard (Power BI / DOMO etc.) | All Streams | Apr'26
43 | BPC | Estate Operation | Apr'26 | 0
44 | BPC | STPIM | Apr'26 | 0
45 | BPC | Fin & Accn | Apr'26 | 0
46 | BW | P2P | Apr'26 | #REF!
47 | BW | STPIM | Apr'26 | 0
48 | BW | Fin & Accn | Apr'26 | 0
49 | BW | OTB | Apr'26 | #REF!
50 | BW | EDM | Apr'26 | 0
51 | DOTMS | Estate Operation | Apr'26 | #REF!
52 | DOTMS | Asset Maintenance | Apr'26 | 0
53 | DOTMS | TMS | Apr'26 | 0
54 | DOTMS | STPIM | Apr'26 | 0
55 | Blockchain | STPIM | Apr'26 | #REF!
56 | HEX | P2P | Apr'26 | #REF!
57 | HEX | STPIM | Apr'26 | #REF!
58 | HEX | OTB | Apr'26 | #REF!
59 | HEX | Fin & Accn | Apr'26 | 0
60 | HEX | EDM | Apr'26 | 0
61 | BSC | N/A | Apr'26
62 | eBAPA | Estate Operation | Apr'26 | #REF!
63 | Estate master data hierarchy | Estate Operation | Apr'26 | 0
64 | Estate operational metric | Estate Operation | Apr'26 | 0
65 | LIS | P2P | Apr'26 | 0
66 | LIS | Trading | Apr'26 | 0
67 | WB DS | TMS | Apr'26 | 0
68 | WB DS | Trading | Apr'26 | 0
69 | WB DS | STPIM | Apr'26 | 0
70 | WB DS | EDM | Apr'26 | 0
71 | WB oleo/socimas | TMS | Apr'26 | 0
72 | WB oleo/socimas | Trading | Apr'26 | 0
73 | WB oleo/socimas | STPIM | Apr'26 | 0
74 | WB oleo/socimas | EDM | Apr'26 | 0
75 | Quality Window | P2P | Apr'26 | 0
76 | Quality Window | Trading | Apr'26 | 0
77 | e-BAST | Asset Maintenance | Apr'26 | 0
78 | e-BAST | P2P | Apr'26 | #REF!
79 | e-BAST | TMS | Apr'26 | 0
80 | e-BAST | STPIM | Apr'26 | 0
81 | e-BAST | OTB | Apr'26 | 0
82 | COPS | TMS | Apr'26 | 0
83 | COPS | Trading | Apr'26 | 0
84 | JIMS | TMS | Apr'26 | 0
85 | JIMS | Trading | Apr'26 | 0
86 | MIGLI | Asset Maintenance | Apr'26 | #REF!
87 | MIGLI | TMS | Apr'26 | 0
88 | CILT | Asset Maintenance | Apr'26 | #REF!
89 | BASYS | STPIM | Apr'26 | 0
90 | ASRS (vendor) | STPIM | Apr'26 | 0
91 | ePO | STPIM | Apr'26 | 0
92 | SmartTrace | STPIM | Apr'26 | 0
93 | Mass Balance | STPIM | Apr'26 | 0
94 | Vendor evaluation | STPIM | Apr'26 | 0
95 | DAMIMAS | OTB | Apr'26 | 0
96 | Doc tracking | OTB | Apr'26 | 0
97 | LC | Fin & Accn | Apr'26 | 0
98 | PL overview | Fin & Accn | Apr'26 | 0
99 | DiFi | Fin & Accn | Apr'26 | 0
100 | Supplier financing | Fin & Accn | Apr'26 | 0
101 | Asset handheld | Fin & Accn | Apr'26 | 0
102 | FR automation | Fin & Accn | Apr'26 | 0
103 | Coretax | Fin & Accn | Apr'26 | 0
104 | eBanking | Fin & Accn | Apr'26 | 0
105 | Tungsten | Fin & Accn | Apr'26 | 0
106 | CRQ | EDM | Apr'26 | 0
107 | PTA approval |  | Apr'26
108 | SPK form |  | Apr'26
109 | MDG |  | Apr'26
110 | GRC |  | Apr'26
111 | AIMS | Asset Maintenance | Apr'26 | #REF!

## 11. Solution Integration (hidden)
# | Application Name | Stream | When | Status | Remarks
1 | Remedy/Helix, KUBE | Asset Maintenance | Apr'26 | 0
2 | Remedy/Helix, KUBE | STPIM | Apr'26 | 0
3 | Remedy/Helix, KUBE | OTB | Apr'26 | 0
4 | Remedy/Helix, KUBE | Fin & Accn | Apr'26 | 0
5 | Remedy/Helix, KUBE | EDM | Apr'26 | 0
6 | Coupa | TMS | Apr'26 | 0
7 | Coupa | STPIM | Apr'26 | 0
8 | Coupa | OTB | Apr'26 | #REF!
9 | Coupa | EDM | Apr'26 | 0
10 | eFACT | Estate Operation | Apr'26 | 0
11 | eFACT | P2P | Apr'26 | 0
12 | eFACT | STPIM | Apr'26 | 0
13 | eFACT | Fin & Accn | Apr'26 | 0
14 | MES | Asset Maintenance | Apr'26 | #REF!
15 | MES | P2P | Apr'26 | 0
16 | ProInt | Fin & Accn | Apr'26 | 0
17 | New Checkroll | Estate Operation | Apr'26 | 0
18 | New Checkroll | TMS | Apr'26 | 0
19 | New Checkroll | STPIM | Apr'26 | 0
20 | New Checkroll | Fin & Accn | Apr'26 | 0
21 | New Checkroll | EDM | Apr'26 | 0
22 | WB US | Estate Operation | Apr'26 | 0
23 | WB US | TMS | Apr'26 | 0
24 | WB US | Trading | Apr'26 | 0
25 | WB US | STPIM | Apr'26 | 0
26 | WB US | OTB | Apr'26 | 0
27 | WB US | EDM | Apr'26 | 0
28 | SMART WB | TMS | Apr'26 | 0
29 | SMART WB | Trading | Apr'26 | 0
30 | LIMS | P2P | Apr'26 | 0
31 | LIMS | Trading | Apr'26 | 0
32 | iLogs (vendor) | TMS | Apr'26 | 0
33 | iLogs (vendor) | Trading | Apr'26 | 0
34 | iLogs (vendor) | STPIM | Apr'26 | 0
35 | iLogs (vendor) | OTB | Apr'26 | 0
36 | Workday | Fin & Accn | Apr'26 | 0
37 | Workday | EDM | Apr'26 | 0
38 | Esker | N/A | Apr'26
39 | Agiblock | N/A | Apr'26
40 | IDSP/IOM | P2P | Apr'26 | 0
41 | IDSP/IOM | OTB | Apr'26 | 0
42 | Dashboard (Power BI / DOMO etc.) | All Streams | Apr'26
43 | BPC | Estate Operation | Apr'26 | 0
44 | BPC | STPIM | Apr'26 | 0
45 | BPC | Fin & Accn | Apr'26 | 0
46 | BW | P2P | Apr'26 | #REF!
47 | BW | STPIM | Apr'26 | 0
48 | BW | Fin & Accn | Apr'26 | 0
49 | BW | OTB | Apr'26 | #REF!
50 | BW | EDM | Apr'26 | 0
51 | DOTMS | Estate Operation | Apr'26 | #REF!
52 | DOTMS | Asset Maintenance | Apr'26 | 0
53 | DOTMS | TMS | Apr'26 | 0
54 | DOTMS | STPIM | Apr'26 | 0
55 | Blockchain | STPIM | Apr'26 | #REF!
56 | HEX | P2P | Apr'26 | #REF!
57 | HEX | STPIM | Apr'26 | #REF!
58 | HEX | OTB | Apr'26 | #REF!
59 | HEX | Fin & Accn | Apr'26 | 0
60 | HEX | EDM | Apr'26 | 0
61 | BSC | N/A | Apr'26
62 | eBAPA | Estate Operation | Apr'26 | #REF!
63 | Estate master data hierarchy | Estate Operation | Apr'26 | 0
64 | Estate operational metric | Estate Operation | Apr'26 | 0
65 | LIS | P2P | Apr'26 | 0
66 | LIS | Trading | Apr'26 | 0
67 | WB DS | TMS | Apr'26 | 0
68 | WB DS | Trading | Apr'26 | 0
69 | WB DS | STPIM | Apr'26 | 0
70 | WB DS | EDM | Apr'26 | 0
71 | WB oleo/socimas | TMS | Apr'26 | 0
72 | WB oleo/socimas | Trading | Apr'26 | 0
73 | WB oleo/socimas | STPIM | Apr'26 | 0
74 | WB oleo/socimas | EDM | Apr'26 | 0
75 | Quality Window | P2P | Apr'26 | 0
76 | Quality Window | Trading | Apr'26 | 0
77 | e-BAST | Asset Maintenance | Apr'26 | 0
78 | e-BAST | P2P | Apr'26 | #REF!
79 | e-BAST | TMS | Apr'26 | 0
80 | e-BAST | STPIM | Apr'26 | 0
81 | e-BAST | OTB | Apr'26 | 0
82 | COPS | TMS | Apr'26 | 0
83 | COPS | Trading | Apr'26 | 0
84 | JIMS | TMS | Apr'26 | 0
85 | JIMS | Trading | Apr'26 | 0
86 | MIGLI | Asset Maintenance | Apr'26 | #REF!
87 | MIGLI | TMS | Apr'26 | 0
88 | CILT | Asset Maintenance | Apr'26 | #REF!
89 | BASYS | STPIM | Apr'26 | 0
90 | ASRS (vendor) | STPIM | Apr'26 | 0
91 | ePO | STPIM | Apr'26 | 0
92 | SmartTrace | STPIM | Apr'26 | 0
93 | Mass Balance | STPIM | Apr'26 | 0
94 | Vendor evaluation | STPIM | Apr'26 | 0
95 | DAMIMAS | OTB | Apr'26 | 0
96 | Doc tracking | OTB | Apr'26 | 0
97 | LC | Fin & Accn | Apr'26 | 0
98 | PL overview | Fin & Accn | Apr'26 | 0
99 | DiFi | Fin & Accn | Apr'26 | 0
100 | Supplier financing | Fin & Accn | Apr'26 | 0
101 | Asset handheld | Fin & Accn | Apr'26 | 0
102 | FR automation | Fin & Accn | Apr'26 | 0
103 | Coretax | Fin & Accn | Apr'26 | 0
104 | eBanking | Fin & Accn | Apr'26 | 0
105 | Tungsten | Fin & Accn | Apr'26 | 0
106 | CRQ | EDM | Apr'26 | 0
107 | PTA approval |  | Apr'26
108 | SPK form |  | Apr'26
109 | MDG |  | Apr'26
110 | GRC |  | Apr'26
111 | AIMS | Asset Maintenance | Apr'26 | #REF!

## 12. Solution Process Change (hidden)
# | Application Name | Stream | When | Status | Remarks
1 | Remedy/Helix, KUBE | Asset Maintenance | Apr'26 | 0
2 | Remedy/Helix, KUBE | STPIM | Apr'26 | 0
3 | Remedy/Helix, KUBE | OTB | Apr'26 | 0
4 | Remedy/Helix, KUBE | Fin & Accn | Apr'26 | 0
5 | Remedy/Helix, KUBE | EDM | Apr'26 | 0
6 | Coupa | TMS | Apr'26 | 0
7 | Coupa | STPIM | Apr'26 | 0
8 | Coupa | OTB | Apr'26 | #REF!
9 | Coupa | EDM | Apr'26 | 0
10 | eFACT | Estate Operation | Apr'26 | 0
11 | eFACT | P2P | Apr'26 | 0
12 | eFACT | STPIM | Apr'26 | 0
13 | eFACT | Fin & Accn | Apr'26 | 0
14 | MES | Asset Maintenance | Apr'26 | #REF!
15 | MES | P2P | Apr'26 | 0
16 | ProInt | Fin & Accn | Apr'26 | 0
17 | New Checkroll | Estate Operation | Apr'26 | 0
18 | New Checkroll | TMS | Apr'26 | 0
19 | New Checkroll | STPIM | Apr'26 | 0
20 | New Checkroll | Fin & Accn | Apr'26 | 0
21 | New Checkroll | EDM | Apr'26 | 0
22 | WB US | Estate Operation | Apr'26 | 0
23 | WB US | TMS | Apr'26 | 0
24 | WB US | Trading | Apr'26 | 0
25 | WB US | STPIM | Apr'26 | 0
26 | WB US | OTB | Apr'26 | 0
27 | WB US | EDM | Apr'26 | 0
28 | SMART WB | TMS | Apr'26 | 0
29 | SMART WB | Trading | Apr'26 | 0
30 | LIMS | P2P | Apr'26 | 0
31 | LIMS | Trading | Apr'26 | 0
32 | iLogs (vendor) | TMS | Apr'26 | 0
33 | iLogs (vendor) | Trading | Apr'26 | 0
34 | iLogs (vendor) | STPIM | Apr'26 | 0
35 | iLogs (vendor) | OTB | Apr'26 | 0
36 | Workday | Fin & Accn | Apr'26 | 0
37 | Workday | EDM | Apr'26 | 0
38 | Esker | N/A | Apr'26
39 | Agiblock | N/A | Apr'26
40 | IDSP/IOM | P2P | Apr'26 | 0
41 | IDSP/IOM | OTB | Apr'26 | 0
42 | Dashboard (Power BI / DOMO etc.) | All Streams | Apr'26
43 | BPC | Estate Operation | Apr'26 | 0
44 | BPC | STPIM | Apr'26 | 0
45 | BPC | Fin & Accn | Apr'26 | 0
46 | BW | P2P | Apr'26 | #REF!
47 | BW | STPIM | Apr'26 | 0
48 | BW | Fin & Accn | Apr'26 | 0
49 | BW | OTB | Apr'26 | #REF!
50 | BW | EDM | Apr'26 | 0
51 | DOTMS | Estate Operation | Apr'26 | #REF!
52 | DOTMS | Asset Maintenance | Apr'26 | 0
53 | DOTMS | TMS | Apr'26 | 0
54 | DOTMS | STPIM | Apr'26 | 0
55 | Blockchain | STPIM | Apr'26 | #REF!
56 | HEX | P2P | Apr'26 | #REF!
57 | HEX | STPIM | Apr'26 | #REF!
58 | HEX | OTB | Apr'26 | #REF!
59 | HEX | Fin & Accn | Apr'26 | 0
60 | HEX | EDM | Apr'26 | 0
61 | BSC | N/A | Apr'26
62 | eBAPA | Estate Operation | Apr'26 | #REF!
63 | Estate master data hierarchy | Estate Operation | Apr'26 | 0
64 | Estate operational metric | Estate Operation | Apr'26 | 0
65 | LIS | P2P | Apr'26 | 0
66 | LIS | Trading | Apr'26 | 0
67 | WB DS | TMS | Apr'26 | 0
68 | WB DS | Trading | Apr'26 | 0
69 | WB DS | STPIM | Apr'26 | 0
70 | WB DS | EDM | Apr'26 | 0
71 | WB oleo/socimas | TMS | Apr'26 | 0
72 | WB oleo/socimas | Trading | Apr'26 | 0
73 | WB oleo/socimas | STPIM | Apr'26 | 0
74 | WB oleo/socimas | EDM | Apr'26 | 0
75 | Quality Window | P2P | Apr'26 | 0
76 | Quality Window | Trading | Apr'26 | 0
77 | e-BAST | Asset Maintenance | Apr'26 | 0
78 | e-BAST | P2P | Apr'26 | #REF!
79 | e-BAST | TMS | Apr'26 | 0
80 | e-BAST | STPIM | Apr'26 | 0
81 | e-BAST | OTB | Apr'26 | 0
82 | COPS | TMS | Apr'26 | 0
83 | COPS | Trading | Apr'26 | 0
84 | JIMS | TMS | Apr'26 | 0
85 | JIMS | Trading | Apr'26 | 0
86 | MIGLI | Asset Maintenance | Apr'26 | #REF!
87 | MIGLI | TMS | Apr'26 | 0
88 | CILT | Asset Maintenance | Apr'26 | #REF!
89 | BASYS | STPIM | Apr'26 | 0
90 | ASRS (vendor) | STPIM | Apr'26 | 0
91 | ePO | STPIM | Apr'26 | 0
92 | SmartTrace | STPIM | Apr'26 | 0
93 | Mass Balance | STPIM | Apr'26 | 0
94 | Vendor evaluation | STPIM | Apr'26 | 0
95 | DAMIMAS | OTB | Apr'26 | 0
96 | Doc tracking | OTB | Apr'26 | 0
97 | LC | Fin & Accn | Apr'26 | 0
98 | PL overview | Fin & Accn | Apr'26 | 0
99 | DiFi | Fin & Accn | Apr'26 | 0
100 | Supplier financing | Fin & Accn | Apr'26 | 0
101 | Asset handheld | Fin & Accn | Apr'26 | 0
102 | FR automation | Fin & Accn | Apr'26 | 0
103 | Coretax | Fin & Accn | Apr'26 | 0
104 | eBanking | Fin & Accn | Apr'26 | 0
105 | Tungsten | Fin & Accn | Apr'26 | 0
106 | CRQ | EDM | Apr'26 | 0
107 | PTA approval |  | Apr'26
108 | SPK form |  | Apr'26
109 | MDG |  | Apr'26
110 | GRC |  | Apr'26
111 | AIMS | Asset Maintenance | Apr'26 | #REF!

## 13. BSDD Main Stream (hidden)
# | Application Name | Stream | When | Status | Remarks
1 | Remedy/Helix, KUBE | Asset Maintenance | May'26 | 0
2 | Remedy/Helix, KUBE | STPIM | May'26 | 0
3 | Remedy/Helix, KUBE | OTB | May'26 | 0
4 | Remedy/Helix, KUBE | Fin & Accn | May'26 | 0
5 | Remedy/Helix, KUBE | EDM | May'26 | 0
6 | Coupa | TMS | May'26 | 0
7 | Coupa | STPIM | May'26 | 0
8 | Coupa | OTB | May'26 | #REF!
9 | Coupa | EDM | May'26 | 0
10 | eFACT | Estate Operation | May'26 | 0
11 | eFACT | P2P | May'26 | 0
12 | eFACT | STPIM | May'26 | 0
13 | eFACT | Fin & Accn | May'26 | 0
14 | MES | Asset Maintenance | May'26 | #REF!
15 | MES | P2P | May'26 | 0
16 | ProInt | Fin & Accn | May'26 | 0
17 | New Checkroll | Estate Operation | May'26 | On going
18 | New Checkroll | TMS | May'26 | 0
19 | New Checkroll | STPIM | May'26 | 0
20 | New Checkroll | Fin & Accn | May'26 | 0
21 | New Checkroll | EDM | May'26 | 0
22 | WB US | Estate Operation | May'26 | 0
23 | WB US | TMS | May'26 | 0
24 | WB US | Trading | May'26 | 0
25 | WB US | STPIM | May'26 | 0
26 | WB US | OTB | May'26 | 0
27 | WB US | EDM | May'26 | 0
28 | SMART WB | TMS | May'26 | 0
29 | SMART WB | Trading | May'26 | 0
30 | LIMS | P2P | May'26 | 0
31 | LIMS | Trading | May'26 | 0
32 | iLogs (vendor) | TMS | May'26 | 0
33 | iLogs (vendor) | Trading | May'26 | 0
34 | iLogs (vendor) | STPIM | May'26 | 0
35 | iLogs (vendor) | OTB | May'26 | 0
36 | Workday | Fin & Accn | May'26 | 0
37 | Workday | EDM | May'26 | 0
38 | Esker | N/A | May'26
39 | Agiblock | N/A | May'26
40 | IDSP/IOM | P2P | May'26 | 0
41 | IDSP/IOM | OTB | May'26 | 0
42 | Dashboard (Power BI / DOMO etc.) | All Streams | May'26
43 | BPC | Estate Operation | May'26 | On going
44 | BPC | STPIM | May'26 | 0
45 | BPC | Fin & Accn | May'26 | 0
46 | BW | P2P | May'26 | #REF!
47 | BW | STPIM | May'26 | 0
48 | BW | Fin & Accn | May'26 | 0
49 | BW | OTB | May'26 | #REF!
50 | BW | EDM | May'26 | 0
51 | DOTMS | Estate Operation | May'26 | #REF!
52 | DOTMS | Asset Maintenance | May'26 | 0
53 | DOTMS | TMS | May'26 | 0
54 | DOTMS | STPIM | May'26 | 0
55 | Blockchain | STPIM | May'26 | #REF!
56 | HEX | P2P | May'26 | #REF!
57 | HEX | STPIM | May'26 | #REF!
58 | HEX | OTB | May'26 | #REF!
59 | HEX | Fin & Accn | May'26 | 0
60 | HEX | EDM | May'26 | 0
61 | BSC | N/A | May'26
62 | eBAPA | Estate Operation | May'26 | #REF!
63 | Estate master data hierarchy | Estate Operation | May'26 | 0
64 | Estate operational metric | Estate Operation | May'26 | 0
65 | LIS | P2P | May'26 | 0
66 | LIS | Trading | May'26 | 0
67 | WB DS | TMS | May'26 | 0
68 | WB DS | Trading | May'26 | 0
69 | WB DS | STPIM | May'26 | 0
70 | WB DS | EDM | May'26 | 0
71 | WB oleo/socimas | TMS | May'26 | 0
72 | WB oleo/socimas | Trading | May'26 | 0
73 | WB oleo/socimas | STPIM | May'26 | 0
74 | WB oleo/socimas | EDM | May'26 | 0
75 | Quality Window | P2P | May'26 | 0
76 | Quality Window | Trading | May'26 | 0
77 | e-BAST | Asset Maintenance | May'26 | 0
78 | e-BAST | P2P | May'26 | #REF!
79 | e-BAST | TMS | May'26 | 0
80 | e-BAST | STPIM | May'26 | 0
81 | e-BAST | OTB | May'26 | 0
82 | COPS | TMS | May'26 | 0
83 | COPS | Trading | May'26 | 0
84 | JIMS | TMS | May'26 | 0
85 | JIMS | Trading | May'26 | 0
86 | MIGLI | Asset Maintenance | May'26 | #REF!
87 | MIGLI | TMS | May'26 | 0
88 | CILT | Asset Maintenance | May'26 | #REF!
89 | BASYS | STPIM | May'26 | 0
90 | ASRS (vendor) | STPIM | May'26 | 0
91 | ePO | STPIM | May'26 | 0
92 | SmartTrace | STPIM | May'26 | 0
93 | Mass Balance | STPIM | May'26 | 0
94 | Vendor evaluation | STPIM | May'26 | 0
95 | DAMIMAS | OTB | May'26 | 0
96 | Doc tracking | OTB | May'26 | 0
97 | LC | Fin & Accn | May'26 | 0
98 | PL overview | Fin & Accn | May'26 | 0
99 | DiFi | Fin & Accn | May'26 | 0
100 | Supplier financing | Fin & Accn | May'26 | 0
101 | Asset handheld | Fin & Accn | May'26 | 0
102 | FR automation | Fin & Accn | May'26 | 0
103 | Coretax | Fin & Accn | May'26 | 0
104 | eBanking | Fin & Accn | May'26 | 0
105 | Tungsten | Fin & Accn | May'26 | 0
106 | CRQ | EDM | May'26 | 0
107 | PTA approval |  | May'26
108 | SPK form |  | May'26
109 | MDG |  | May'26
110 | GRC |  | May'26
111 | AIMS | Asset Maintenance | May'26 | #REF!

## 14. BSDD Interim Procedure (hidden)
# | Application Name | Stream | When | Status | Remarks
1 | Remedy/Helix, KUBE | Asset Maintenance | May'26 | 0
2 | Remedy/Helix, KUBE | STPIM | May'26 | 0
3 | Remedy/Helix, KUBE | OTB | May'26 | 0
4 | Remedy/Helix, KUBE | Fin & Accn | May'26 | 0
5 | Remedy/Helix, KUBE | EDM | May'26 | 0
6 | Coupa | TMS | May'26 | 0
7 | Coupa | STPIM | May'26 | 0
8 | Coupa | OTB | May'26 | #REF!
9 | Coupa | EDM | May'26 | 0
10 | eFACT | Estate Operation | May'26 | 0
11 | eFACT | P2P | May'26 | 0
12 | eFACT | STPIM | May'26 | 0
13 | eFACT | Fin & Accn | May'26 | 0
14 | MES | Asset Maintenance | May'26 | #REF!
15 | MES | P2P | May'26 | 0
16 | ProInt | Fin & Accn | May'26 | 0
17 | New Checkroll | Estate Operation | May'26 | 0
18 | New Checkroll | TMS | May'26 | 0
19 | New Checkroll | STPIM | May'26 | 0
20 | New Checkroll | Fin & Accn | May'26 | 0
21 | New Checkroll | EDM | May'26 | 0
22 | WB US | Estate Operation | May'26 | 0
23 | WB US | TMS | May'26 | 0
24 | WB US | Trading | May'26 | 0
25 | WB US | STPIM | May'26 | 0
26 | WB US | OTB | May'26 | 0
27 | WB US | EDM | May'26 | 0
28 | SMART WB | TMS | May'26 | 0
29 | SMART WB | Trading | May'26 | 0
30 | LIMS | P2P | May'26 | 0
31 | LIMS | Trading | May'26 | 0
32 | iLogs (vendor) | TMS | May'26 | 0
33 | iLogs (vendor) | Trading | May'26 | 0
34 | iLogs (vendor) | STPIM | May'26 | 0
35 | iLogs (vendor) | OTB | May'26 | 0
36 | Workday | Fin & Accn | May'26 | 0
37 | Workday | EDM | May'26 | 0
38 | Esker | N/A | May'26
39 | Agiblock | N/A | May'26
40 | IDSP/IOM | P2P | May'26 | 0
41 | IDSP/IOM | OTB | May'26 | 0
42 | Dashboard (Power BI / DOMO etc.) | All Streams | May'26
43 | BPC | Estate Operation | May'26 | 0
44 | BPC | STPIM | May'26 | 0
45 | BPC | Fin & Accn | May'26 | 0
46 | BW | P2P | May'26 | #REF!
47 | BW | STPIM | May'26 | 0
48 | BW | Fin & Accn | May'26 | 0
49 | BW | OTB | May'26 | #REF!
50 | BW | EDM | May'26 | 0
51 | DOTMS | Estate Operation | May'26 | #REF!
52 | DOTMS | Asset Maintenance | May'26 | 0
53 | DOTMS | TMS | May'26 | 0
54 | DOTMS | STPIM | May'26 | 0
55 | Blockchain | STPIM | May'26 | #REF!
56 | HEX | P2P | May'26 | #REF!
57 | HEX | STPIM | May'26 | #REF!
58 | HEX | OTB | May'26 | #REF!
59 | HEX | Fin & Accn | May'26 | 0
60 | HEX | EDM | May'26 | 0
61 | BSC | N/A | May'26
62 | eBAPA | Estate Operation | May'26 | #REF!
63 | Estate master data hierarchy | Estate Operation | May'26 | 0
64 | Estate operational metric | Estate Operation | May'26 | 0
65 | LIS | P2P | May'26 | 0
66 | LIS | Trading | May'26 | 0
67 | WB DS | TMS | May'26 | 0
68 | WB DS | Trading | May'26 | 0
69 | WB DS | STPIM | May'26 | 0
70 | WB DS | EDM | May'26 | 0
71 | WB oleo/socimas | TMS | May'26 | 0
72 | WB oleo/socimas | Trading | May'26 | 0
73 | WB oleo/socimas | STPIM | May'26 | 0
74 | WB oleo/socimas | EDM | May'26 | 0
75 | Quality Window | P2P | May'26 | 0
76 | Quality Window | Trading | May'26 | 0
77 | e-BAST | Asset Maintenance | May'26 | 0
78 | e-BAST | P2P | May'26 | #REF!
79 | e-BAST | TMS | May'26 | 0
80 | e-BAST | STPIM | May'26 | 0
81 | e-BAST | OTB | May'26 | 0
82 | COPS | TMS | May'26 | 0
83 | COPS | Trading | May'26 | 0
84 | JIMS | TMS | May'26 | 0
85 | JIMS | Trading | May'26 | 0
86 | MIGLI | Asset Maintenance | May'26 | #REF!
87 | MIGLI | TMS | May'26 | 0
88 | CILT | Asset Maintenance | May'26 | #REF!
89 | BASYS | STPIM | May'26 | 0
90 | ASRS (vendor) | STPIM | May'26 | 0
91 | ePO | STPIM | May'26 | 0
92 | SmartTrace | STPIM | May'26 | 0
93 | Mass Balance | STPIM | May'26 | 0
94 | Vendor evaluation | STPIM | May'26 | 0
95 | DAMIMAS | OTB | May'26 | 0
96 | Doc tracking | OTB | May'26 | 0
97 | LC | Fin & Accn | May'26 | 0
98 | PL overview | Fin & Accn | May'26 | 0
99 | DiFi | Fin & Accn | May'26 | 0
100 | Supplier financing | Fin & Accn | May'26 | 0
101 | Asset handheld | Fin & Accn | May'26 | 0
102 | FR automation | Fin & Accn | May'26 | 0
103 | Coretax | Fin & Accn | May'26 | 0
104 | eBanking | Fin & Accn | May'26 | 0
105 | Tungsten | Fin & Accn | May'26 | 0
106 | CRQ | EDM | May'26 | 0
107 | PTA approval |  | May'26
108 | SPK form |  | May'26
109 | MDG |  | May'26
110 | GRC |  | May'26
111 | AIMS | Asset Maintenance | May'26 | #REF!